## TSA
Checklist - focus on Day 1
TSA |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Assessment of Service needs
Review existing TSA schedules developed by Xella | TSA | Day 1 | No
Develop a TSA tracker listing out for each TSA, the scope of services, related function, service fees, duration, location, TSA owners etc. | TSA | Day 1 | No
Conduct interviews with each function at Fermacell to identify services currently provided by Xella to Fermacell | TSA | Day 1 | No
Determine services provided by Xella teams that are not transferring with the deal | TSA | Day 1 | No
Determine services provided by Xella to Fermacell that could be provided in-house by Fermacell | TSA | Day 1 | No
Conduct interviews with James Hardie functions to determine services that James Hardie can provide to replace those provided by Xella | TSA | Day 1 | No
Develop list if services for which Transition Services Agreements will be needed | TSA | Day 1 | No
Identify gaps between services in the TSA schedule provided by Xella and those identified through interviews with functional leads from James Hardie and Fermacell | TSA | Day 1 | No
Validate the services for which support will be required through TSAs with each functional lead at Fermacell, James Hardie, and Xella | TSA | Day 1 | No
Schedule of TSA services
Conduct interviews with Fermacell functional leads to develop detailed scope of services to be provided under each TSA | TSA | Day 1 | No
Identify locations at which TSAs are needed as well as TSA duration | TSA | Day 1 | No
Legal team to draft TSA schedules for each service that Xella will need to provide, if TSA schedule does not already exist | TSA | Day 1 | No
Legal team to modify existing TSA schedules based on feedback from functional leads from James Hardie and Fermacell functional leads | TSA | Day 1 | No
Discuss updated TSA schedule with Xella through executive steering committee meetings | TSA | Day 1 | No
Modify TSA schedules as needed based on feedback from functional leads | TSA | Day 1 | No
Review modified TSA schedules with functional leads from James Hardie, Fermacell and Xella and get sign off from all parties | TSA | Day 1 | No
Draft final (execution version) of TSA schedule to be signed at deal close | TSA | Day 1 | No
Governance and Invoicing Process
Identify TSA owners from Xella (Service Provider) and James Hardie/Fermacell (Service Recipient) | TSA | Day 1 | No
Develop a TSA governance process based on terms in the Form of Transition Services | TSA | Day 1 | No
Review the governance process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties | TSA | Day 1 | No
Develop a process to calculate TSA fees on a monthly basis and to generate invoices | TSA | Day 1 | No
Review the invoicing process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties | TSA | Day 1 | No
TSA Exit Planning (NEW)
Define TSA exit criteria and transition milestones for each service | TSA | Day 1 | No
Identify stranded costs associated with TSA exits | TSA | Day 1 | No |  |  |  | FP&A |  | High
Develop TSA exit readiness assessment process | TSA | Day 60-120 | No
Create TSA wind-down communication plan with seller | TSA | Day 60-120 | No |  |  |  | Legal
Track TSA cost vs. internal capability build costs | TSA | Day 60-120 | No |  |  |  | FP&A |  | Medium
Execute TSA termination notices per contractual requirements | TSA | Year 1-2 | No |  |  |  | Legal |  | High
Complete knowledge transfer from TSA providers | TSA | Year 1-2 | No |  |  |  | All Functions |  | High

## Consolidation & Ext. Repo
Checklist - focus on Day 1
Consolidation & External Reporting |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Mobilization and data gathering
Understand current James Hardie and Fermacell org structures including roles and responsibilities | Consolidation & Ext Reporting | Day 1
Identify key contacts/counterparts across the regions | Consolidation & Ext Reporting | Day 1
Gather and share org chart, chart of accounts, entity listing, currencies, etc. between Fermacell and James Hardie | Consolidation & Ext Reporting | Day 1
Consolidation - close the books
Obtain policies and procedures on monthly close and close schedule with cut-offs and timing | Consolidation & Ext Reporting | Day 1
Establish the NewCo financial close calendar | Consolidation & Ext Reporting | Day 1
Review functional currencie of all Fermacells entities and address changes, as needed | Consolidation & Ext Reporting | Day 1
Develop task list for monthly consolidation combined company close | Consolidation & Ext Reporting | Day 1
Develop contingency plan for potential mid-month close(i.e., stub period) dependent on anti-trust approvals | Consolidation & Ext Reporting | Day 1
Review task list for monthly / quarterly reporting | Consolidation & Ext Reporting | Day 1
Document trial balance submission timing to align with Fermacell entities | Consolidation & Ext Reporting | Day 1
Test upload/input format file | Consolidation & Ext Reporting | Day 1
Perform trial balances submission in consolidation system | Consolidation & Ext Reporting | Day 1
Day 1 consolidation model / chart of account mapping
Understand the IT landscape for consolidation and reporting structures by product line and geographical area | Consolidation & Ext Reporting | Day 1
Understand James Hardie / Fermacell consolidation procedures (upload, journal entries, etc.) | Consolidation & Ext Reporting | Day 1
Understand Fermacell account structure (custom dimensions, cost center, etc.) | Consolidation & Ext Reporting | Day 1
Establish future state legal entity and reporting structure for combined company | Consolidation & Ext Reporting
Create org structure/codes in consolidation system based on legal/tax structure | Consolidation & Ext Reporting | Day 1
Review Fermacell chart of accounts and identifes differences | Consolidation & Ext Reporting | Day 1
Develop the approach to managing multiple chart of accounts | Consolidation & Ext Reporting | Day 1
Determine approach for chart of account mapping between Fermacell/James Hardie (Fermacell Oracle to James Hardie Oracle, Fermacell Oracle to James Hardie Hyperion) | Consolidation & Ext Reporting | Day 1
Map Fermacell chart of accounts to James Hardie chart of accounts | Consolidation & Ext Reporting | Day 1
Identify new accounts to be created,closed or renamed | Consolidation & Ext Reporting | Day 1
Identify I/C accounts to assign intercompany partner | Consolidation & Ext Reporting | Day 1
Map intercompany accounts to intercompany partner | Consolidation & Ext Reporting | Day 1
Review preliminary mapping with technical accounting and flag accounts requiring attention | Consolidation & Ext Reporting | Day 1
Communicate with reporting FP&A teams to understand reporting requirements/decisions | Consolidation & Ext Reporting | Day 1
Consider impact of further system implementation on mapping (e.g. Hyperion redesign) | Consolidation & Ext Reporting | Day 1
Build of FDM Mapping Tables | Consolidation & Ext Reporting | Day 1
Test and validate mapping tables | Consolidation & Ext Reporting | Day 1
Training and access
Provide system access, as necessary | Consolidation & Ext Reporting | Day 1
Train identified employees on system applications | Consolidation & Ext Reporting | Day 1
Intercompany elimination
Perform inventory of I/C relationships | Consolidation & Ext Reporting | Day 1
Assess integration impact on current and expected intercompany transactions | Consolidation & Ext Reporting | Day 1
Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.) | Consolidation & Ext Reporting | Day 1
Understand multi-arrangements transactions and assess materiality, if any | Consolidation & Ext Reporting | Day 1
Assess current process for capturing intercompany activity and assess applicability to current business requirements | Consolidation & Ext Reporting | Day 1
Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell | Consolidation & Ext Reporting | Day 1
Create new intercompany trading partners and accounts | Consolidation & Ext Reporting | Day 1
Purchase accounting and corporate policies
Obtain listing of purchase accounting adjustments based on draft and final valuation reports | Consolidation & Ext Reporting | Day 1
Determine approach and confirm push-down level of purchase accounting entries (entity, country, regional, corporate) | Consolidation & Ext Reporting | Day 1
Confirm feasibility and document push-down approach | Consolidation & Ext Reporting | Day 1
Policies, procedures, and documentation
Collect and review all policies, standards and procedures | Consolidation & Ext Reporting | Day 1
Perform policy gap analysis to understand accounting difference between Fermacell and James Hardie | Consolidation & Ext Reporting | Day 1
Assess materiality of difference in accounting policy | Consolidation & Ext Reporting | Day 1
Understand new accounting policies required as result of the merger | Consolidation & Ext Reporting | Day 1
Prioritize accounting policies to be developed requiring Day 1 alignment | Consolidation & Ext Reporting | Day 1
Develop revised or common policies and procedures | Consolidation & Ext Reporting | Day 1
Obtain approval from policy steering committee | Consolidation & Ext Reporting | Day 1
Train employees and implent policies | Consolidation & Ext Reporting
SEC & other regulatory reporting readiness
Identify main differences between James Hardie and Fermacell disclosures | Consolidation & Ext Reporting | Day 1
Identify new accounts to be created to support SEC disclosures/accounts roll forward | Consolidation & Ext Reporting | Day 1
Prepare historical combined company financial statements and key performance indicators | Consolidation & Ext Reporting | Day 1
Develop plan to produce 8-K reporting required Day 4 post-close and identify data requirements | Consolidation & Ext Reporting | Day 1
Develop plan to produce Offering Memorandum (OM) post-close and identify data requirements | Consolidation & Ext Reporting | Day 1
Agree upon NewCo financial statement reporting requirements | Consolidation & Ext Reporting | Day 1
Determine James Hardie and Fermacell’s Day 1 reporting segments | Consolidation & Ext Reporting | Day 1
Draft outline of NewCo interim financial statements for review | Consolidation & Ext Reporting | Day 1
Draft purchase accounting footnote | Consolidation & Ext Reporting | Day 1
Draft pro forma financial statements | Consolidation & Ext Reporting | Day 1
Develop merger related disclosures (e.g., stock compensation) | Consolidation & Ext Reporting | Day 1
Submit Offering Memorandum (OM) post- Day 1 | Consolidation & Ext Reporting | Day 1
Submit amended 8-KA with financials within 75 days post-close | Consolidation & Ext Reporting | Day 60-120
Define post-Day 1data requirements to integrated reporting | Consolidation & Ext Reporting | Day 60-120
Reporting - statutory
Understand current system processes to perform statutory reports | Consolidation & Ext Reporting | Day 1
Inventory all reporting requirements and status of each | Consolidation & Ext Reporting | Day 1
Update inventory based upon local legal merger | Consolidation & Ext Reporting | Day 1
Determine valuation requirements for local tax mergers | Consolidation & Ext Reporting | Day 1
Engage appraiser, as necessary | Consolidation & Ext Reporting | Day 1
Structure opening balance sheet accounting based upon local legal merger plan | Consolidation & Ext Reporting | Day 1
Link transaction accounting to local legal merger plan | Consolidation & Ext Reporting | Day 1
Reporting - management
Obtain both company close packages and identify unique key performance indicators | Consolidation & Ext Reporting | Day 1
Understand current reporting responsibilities, systems and processes | Consolidation & Ext Reporting | Day 1
Agree upon the combined company key performance indicators for reporting purposes | Consolidation & Ext Reporting | Day 1
Validate availability of information within accounting close function | Consolidation & Ext Reporting | Day 1
Review key performance indicators and management reporting package with investor relations | Consolidation & Ext Reporting | Day 1
Design the combined company interim close packages | Consolidation & Ext Reporting | Day 1
Agree upon reporting requirements and key stakeholders (including credit agencies and other reporting needs) | Consolidation & Ext Reporting | Day 1
Train personnel on financial information available and discussion/narrative requirements | Consolidation & Ext Reporting | Day 1
Statement of cash flow
Review and compare James Hardie and Fermacell cash flow statement models and identify gaps | Consolidation & Ext Reporting | Day 1
Develop process to produce combined statement of cash flows | Consolidation & Ext Reporting | Day 1
Prepare combined cash flow statement for SEC filing | Consolidation & Ext Reporting | Day 1
Pro Forma & Synergy Modeling (NEW)
Develop pro forma financial model for combined entity | Consolidation & Ext Reporting | Day 1 |  |  |  |  | FP&A |  | High
Create model of expected revenue synergies and cost savings | Consolidation & Ext Reporting | Day 1 |  |  |  |  | FP&A, Corp Dev |  | High
Establish data retention protocols for acquired company financial data | Consolidation & Ext Reporting | Day 1 |  |  |  |  | IT, Legal |  | High
IFRS / GAAP Alignment (if cross-border)
Identify IFRS vs. GAAP accounting differences between entities | Consolidation & Ext Reporting | Day 1 |  |  |  |  | Technical Accounting |  | High
Develop IFRS/GAAP reconciliation procedures | Consolidation & Ext Reporting | Day 1 |  |  |  |  | Technical Accounting |  | High
Determine reporting framework for combined entity | Consolidation & Ext Reporting | Day 1 |  |  |  |  | Legal, Technical Accounting |  | High
Data Governance (NEW)
Audit acquired company's financial data quality and completeness | Consolidation & Ext Reporting | Day 1 |  |  |  |  | IT, Internal Audit |  | High
Establish combined company data governance framework | Consolidation & Ext Reporting | Day 60-120 |  |  |  |  | IT, Finance |  | Medium
Define master data management approach for combined entity | Consolidation & Ext Reporting | Day 60-120 |  |  |  |  | IT |  | Medium

## Operational Accounting
Checklist - focus on Day 1
Operational Accounting |  | Last updated: | DRAFT LOG
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to Client | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
General Ledger - close the books
Obtain policies and procedures on monthly close and close schedule with cut-offs and timing | Operational Accounting | Day 1 | [7 empty] | Not started
Identify and manage differences in chart of accounts | Operational Accounting | Day 1 | [7 empty] | Not started
Develop the approach to managing multiple chart of accounts | Operational Accounting | Day 1 | [7 empty] | Not started
Identify tools needed to perform the monthly consolidation | Operational Accounting | Day 1 | [7 empty] | Not started
Establish the interim combined company financial close calendar | Operational Accounting | Day 1 | [7 empty] | Not started
Develop contingency plan based upon different deal close date scenarios | Operational Accounting | Day 1 | [7 empty] | Not started
Assess opportunity for close process improvement | Operational Accounting | Day 1
Adjust the close processes incrementally | Operational Accounting | Day 60-120
Align the accounting close with strategic priorities | Operational Accounting | Day 60-120
Establish improved NewCo financial close calendar | Operational Accounting | Day 60-120 | [7 empty] | Not started
Payroll
Assess current state processes | Operational Accounting | Day 1 | [7 empty] | Not started
Confirm listing of employees census, geographical location and legal entity structuring | Operational Accounting | Day 1
Plan enrollment procedures for Day 1 acquired employees | Operational Accounting | Day 1 | [7 empty] | Not started
Determine systems required to manage Fermacell payroll functions of Day 1 | Operational Accounting | Day 1 | [7 empty] | Not started
Develop interim operating model for Day 1 | Operational Accounting | Day 1 | [7 empty] | Not started
Understand downstream benefit accounting impacts based on HR decisions | Operational Accounting | Day 1 | [7 empty] | Not started
Migrate payroll data sets to integrated system | Operational Accounting | Day 60-120 | [7 empty] | Not started
Establish fully integrate payroll processing function | Operational Accounting | Year 1-2 | [7 empty] | Not started
Accounts payable
Understand current A/P processing (domestic and international) | Operational Accounting | Day 1 | [7 empty] | Not started
Identify responsibility for payables processing for Day 1 | Operational Accounting | Day 1 | [7 empty] | Not started
Identify opportunities to consolidate efforts for accounts payable (domestic and international) | Operational Accounting | Day 60-120 | [7 empty] | Not started
Standardize approach for timing of payments (i.e., frequency of check cuts and discounts) | Operational Accounting | Day 60-120 | [7 empty] | Not started
Accounts payable - travel and entertainment reimbursement and employee policies
Identify responsibility for processing time and expenses | Operational Accounting | Day 1 | [7 empty] | Not started
Determine and develop approach to time and expense reimbursement (e.g., through direct deposit, with normal paycheck, or separate run) | Operational Accounting | Day 1 | [7 empty] | Not started
Communicate travel and expense policies and procedures corporate wide | Operational Accounting | Day 1 | [7 empty] | Not started
Implement T&E control framework/policy | Operational Accounting | Day 60-120 | [7 empty] | Not started
Accounts receivable - billing
Develop the combined invoicing process under NewCo | Operational Accounting | Day 1 | [7 empty] | Not started
Determine intracompany invoicing currency | Operational Accounting | Day 1 | [7 empty] | Not started
Generate an update letter for customers with NewCo name change. Coordinate with company announcement. | Operational Accounting | Day 1 | [7 empty] | Not started
Develop communication plan for sales team for invoicing practices | Operational Accounting | Day 1 | [7 empty] | Not started
Determine updated sales tax requirements | Operational Accounting | Day 1 | [7 empty] | Not started
Define returns and billing adjustment policies | Operational Accounting | Day 1 | [7 empty] | Not started
Accounts receivable - credit and collections
Understand differences in credit policies | Operational Accounting | Day 1 | [7 empty] | Not started
Review credit files and evaluate major creditors for any new exposures | Operational Accounting | Day 1 | [7 empty] | Not started
Evaluate credit limits for common customers and determine the combined company credit limit | Operational Accounting | Day 1 | [7 empty] | Not started
Standardize the credit approval and documentation process | Operational Accounting | Day 1 | [7 empty] | Not started
Identify differences in "account overdue" definition and standardize | Operational Accounting | Day 1 | [7 empty] | Not started
Identify differences in the collection process and standardize | Operational Accounting | Day 1 | [7 empty] | Not started
Consolidate credit collections agents | Operational Accounting | Day 1 | [7 empty] | Not started
Establish a consistent write off policy | Operational Accounting | Day 1 | [7 empty] | Not started
Revenue recognition policies
Identify revenue recognition methodology differences between companies and determine Day 1 policy | Operational Accounting | Day 1 | [7 empty] | Not started
Determine how any revenue recognition methodology changes impact the current sales and contracting process | Operational Accounting | Day 1 | [7 empty] | Not started
Update standard contracts, as necessary | Operational Accounting | Day 1 | [7 empty] | Not started
Determine combined company ales model and cummuncate with field sales team | Operational Accounting | Day 1 | [7 empty] | Not started
Identify any issues between the proposed sales model to the proposed revenue recognition methodology | Operational Accounting | Day 1 | [7 empty] | Not started
Identify any contracting conflicts caused by the proposed sales model | Operational Accounting | Day 1 | [7 empty] | Not started
Work with Sales Management to revise sales models and methodologies for revenue recognition and contracting | Operational Accounting | Day 1 | [7 empty] | Not started
Train and implement amended receivable policies | Operational Accounting | Day 1 | [7 empty] | Not started
Identify opportunities to consolidate efforts for accounts receivable (domestic and international) | Operational Accounting | Day 60-120 | [7 empty] | Not started
Cash management
Perform bank account reconciliation and consolidation | Operational Accounting | Day 1 | [7 empty] | Not started
Update and finalize Day 1 banking requirements | Operational Accounting | Day 1 | [7 empty] | Not started
Ensure Day 1 funding and purchase accounting | Operational Accounting | Day 1
Identify long-term cash management responsibility (signing, bank notification) and implement cash management functionality (bank, auto or manual) | Operational Accounting | Day 1 | [7 empty] | Not started
Identify any 3rd party debt and payment requirements | Operational Accounting | Day 1 | [7 empty] | Not started
Wire and electronic transfers
Identify IT requirements for Day 1 wire transfers and implement (auto or manual) | Operational Accounting | Day 1 | [7 empty] | Not started
Update and communicate new signature process | Operational Accounting | Day 1 | [7 empty] | Not started
Identify required vendor wire transfers and confirm set up | Operational Accounting | Day 1 | [7 empty] | Not started
Intercompany elimination
Perform inventory of I/C relationships | Operational Accounting | Day 1
Assess integration impact on current and expected intercompany transactions | Operational Accounting | Day 1
Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.) | Operational Accounting | Day 1
Understand multi-arrangements transactions and assess materiality, if any | Operational Accounting | Day 1
Assess current process for capturing intercompany activity and assess applicability to current business requirements | Operational Accounting | Day 1
Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell | Operational Accounting | Day 1
Create new intercompany trading partners and accounts | Operational Accounting | Day 1
Fixed assets
Assess current but not yet started projects | Operational Accounting | Day 1 | [7 empty] | Not started
Determine if a fixed asset inventory is required and implement if necessary (coordinate with IT for IT hardware) | Operational Accounting | Day 1 | [7 empty] | Not started
Develop approach to managing assets that will be disposed of on Day 1, if applicable | Operational Accounting | Day 1 | [7 empty] | Not started
Standardize procedures for asset retirement and disposal | Operational Accounting | Day 1 | [7 empty] | Not started
Standardize capitalization policies and procedures | Operational Accounting | Day 1 | [7 empty] | Not started
Standardize depreciation methods | Operational Accounting | Day 1 | [7 empty] | Not started
Projects and Initiatives
Identify all projects and initiatives (capex and other) in progress or about to be launched and review with respect to NewCo structure and objectives. Rationalize if required | Operational Accounting | Day 1 | [7 empty] | Not started
Identify critical projects and launches that need to managed through the transition to minimize risk of failure | Operational Accounting | Day 1 | [7 empty] | Not started
Review all current major projects for compliance with delivery dates | Operational Accounting | Day 1 | [7 empty] | Not started
Review all current major projects for cost status versus budget and forecast | Operational Accounting | Day 1 | [7 empty] | Not started
Ensure project reporting systems provide adequate management information | Operational Accounting | Day 1 | [7 empty] | Not started
Inventory
Assess current inventory policies and processes (reserves, returns, costing) | Operational Accounting | Day 1 | [7 empty] | Not started
Align material differences in accounting policy | Operational Accounting | Day 1 | [7 empty] | Not started
Conduct inventory valuations, as required | Operational Accounting | Day 1
Contracts
Review any exclusive purchasing agreements or preferred supplier for conflicts | Operational Accounting | Day 1
Review payment terms and determine what actions, if any, need to take place | Operational Accounting | Day 1

## Internal Controls
Checklist - focus on Day 1
Internal Controls |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Internal Audit
Assist management by evaluating the design and effectiveness of critical operating controls and estblish remediation strategies. | Internal Audit | Day 1
Develop an understanding of Fermacell's SOX and IA programs and prior year SOX/IA results. | Internal Audit | Day 1
Plan 2018 Fermacell controls testing strategy to support 2018 EY substantive audit activities | Internal Audit | Day 1
Assist management with designing and implementing acquisition transaction controls (e.g., FCR, Treasury, Tax) | Internal Audit | Day 1
Understand requirements defined in TSA and perform a risk evaluation. | Internal Audit | Day 1
Determine IA staffing/cosource needs including longer term audit department structure and short term needs for SOX requirements. | Internal Audit | Day 1
Conduct Fermacell Risk Assessment | Internal Audit | Day 30
Execute 2018 Fermacell controls testing, to support EY substantive audit activities. | Internal Audit | Day 100
Conduct New Co. risk assessment while leveraging Fermacell risk assessment results. | Internal Audit | Day 100
Define the future SOX plan for New Co. | Internal Audit | Day 100
Refine existing 302 certification plan | Internal Audit | Day 100
Conduct a TSA compliance audit for high risk areas. | Internal Audit | Day 100
Execute audits supporting regulatory compliance including EU Safe Harbor and Conflict Minerals) | Internal Audit | Day 100
Evaluate and purchase an IA/SOX document retention tool. | Internal Audit | Day 100
Controls for Integration Activities (NEW)
Design controls for new intercompany transactions | Internal Audit | Day 1 |  |  |  |  | Operational Accounting |  | High
Assess IT General Controls (ITGC) for acquired systems | Internal Audit | Day 1 |  |  |  |  | IT |  | High
Conduct fraud risk assessment for combined entity | Internal Audit | Day 1 |  |  |  |  | Finance Leadership |  | High
Review segregation of duties in combined finance organization | Internal Audit | Day 60-120 |  |  |  |  | HR, Finance |  | High
Integrate acquired entity into SOX testing program | Internal Audit | Day 60-120 | [6 empty] | High
Establish unified control monitoring and remediation process | Internal Audit | Day 60-120 | [6 empty] | Medium
Assess purchase accounting controls and journal entry review | Internal Audit | Day 1 |  |  |  |  | Consolidation |  | High
Review access controls for combined financial systems | Internal Audit | Day 60-120 |  |  |  |  | IT |  | High
Develop combined entity internal audit plan | Internal Audit | Year 1-2 | [6 empty] | Medium

## Income Tax
Checklist - focus on Day 1
Tax |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Organization and Governance
Determine combined James Hardie Tax department structure and accountability requirements for Day One | Income Tax | Day 1
Train staff on Day One Tax processes, as needed | Income Tax | Day 1
Tax Compliance
Identify Enterprise global tax processes and compliance and provision obligations | Income Tax | Day 1
Understand acquisition impact on local tax compliance obligations in each key/material tax jurisdiction | Income Tax | Day 1
Complete required tax filings | Income Tax | Day 1
Update global compliance calendars for new reporting requirements | Income Tax | Day 1
Ensure tax payments can be made globally | Income Tax | Day 1
Determine Enterprise tax accounting methods and requirements to align to James Hardie accounting methods (i.e. deferred taxes) | Income Tax | Day 1
Obtain tax depreciation information/schedules for all required assets as of transaction close | Income Tax | Day 1
Obtain and file Enterprise historical tax filing and audit data to James Hardie (electronic and paper) | Income Tax | Day 1
Assess Enterprise tax systems and determine integration plan | Income Tax | Day 1
Transfer Pricing & Intercompany (NEW)
Develop transfer pricing documentation for new intercompany flows | Income Tax | Day 1 |  |  |  |  | Treasury |  | High
Analyze tax attribute carryforwards (NOLs, credits) for acquired entity | Income Tax | Day 1 | [6 empty] | High
Assess Section 382/383 limitations on acquired tax attributes | Income Tax | Day 1 |  |  |  |  | Legal |  | High
Indirect Tax (NEW)
Review VAT/GST registration changes required post-transaction | Income Tax | Day 1 |  |  |  |  | Legal |  | High
Assess indirect tax implications of legal entity restructuring | Income Tax | Day 1 |  |  |  |  | Legal, Treasury |  | High
Update sales and use tax nexus analysis for combined entity | Income Tax | Day 60-120 |  |  |  |  | Operational Accounting |  | Medium
Integrate indirect tax compliance into combined close process | Income Tax | Day 60-120 |  |  |  |  | Consolidation |  | Medium
Align customs and import/export duty processes | Income Tax | Day 60-120 |  |  |  |  | Operations |  | Medium

## Facilities & Indirect Sourcing
Checklist - focus on Day 1
Facilities and Indirect Sourcing |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Facilities
Complete diligence on existing Real Estate organization | Facilities & Indirect Sourcing | Day 1
Design Day One and interim state organization structure | Facilities & Indirect Sourcing | Day 1
Estimate synergies related to Day One and interim organization structure | Facilities & Indirect Sourcing | Day 1
Inventory and map total real estate holdings | Facilities & Indirect Sourcing | Day 1
Collaborate with org design team to understand facility requirements | Facilities & Indirect Sourcing | Day 1
Complete review of corporate locations for optimization planning | Facilities & Indirect Sourcing | Day 1
Review leases on properties that may be exited post-transaction close to determine if early termination provision exists | Facilities & Indirect Sourcing | Day 1
Determine landlords requiring notification or consent letters prior to transaction close | Facilities & Indirect Sourcing | Day 1
Notifications and consent letters for required landlords sent out and consent letters received | Facilities & Indirect Sourcing | Day 1
Determine go-forward future data management tool for Real Estate of combined company | Facilities & Indirect Sourcing | Day 1
Assume lease ownership for sites that are leased by Xella and are being transferred to James Hardie | Facilities & Indirect Sourcing | Day 1
Ensure flawless transition and harmonization of facilities management and maintenance | Facilities & Indirect Sourcing | Day 1
Ensure appropriate security access changes are reflected in facilities | Facilities & Indirect Sourcing | Day 1
Complete migration to single / optimal Real Estate data management tool | Facilities & Indirect Sourcing | Day 60-120
Alignment / harmonization of core Real Estate policies, processes & procedures | Facilities & Indirect Sourcing | Day 60-120
Implement new combined organization structure | Facilities & Indirect Sourcing | Day 60-120
Negotiate lease terminations, concessions and other agreements with landlords to support the real estate consolidation process | Facilities & Indirect Sourcing | Day 60-120
Complete survey of properties to determine sign ordinance and approval requirements for new signage | Facilities & Indirect Sourcing | Day 60-120
Indirect Sourcing
Review and rationalize current indirect spend | Facilities & Indirect Sourcing | Day 1
Complete review / diligence on current vendor sourcing and outsourcing contracts | Facilities & Indirect Sourcing | Day 1
Revised synergy & one-time cost estimates based on diligence findings | Facilities & Indirect Sourcing | Day 1
Review existing vendors for capabilities, quality, and compliance with corporate standards | Facilities & Indirect Sourcing | Day 1
Create and implement a supplier vendor certification process | Facilities & Indirect Sourcing | Day 1
Achieve optimal vendor sourcing for combined company | Facilities & Indirect Sourcing | Day 1
Assess current state metrics and reporting process | Facilities & Indirect Sourcing | Day 1
Develop and implement new metrics and reporting capabilities | Facilities & Indirect Sourcing | Day 60-120

## Treasury & Risk Mgmt
Checklist - focus on Day 1
Treasury and Risk Management |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Organization and Governance
Complete Day One staffing requirements for combined Treasury | Treasury / Risk Management | Day 1
Determine Gaps in Treasury's polices and procedures | Treasury / Risk Management | Day 1
Establish combined Treasury policies and controls | Treasury / Risk Management | Day 1
Train Enterprise staff on Day One Treasury processes, as needed | Treasury / Risk Management | Day 1
Financing and Investing
Develop a detailed cash flow forecast for pre-acquisition and year one activities |  | Day 1
Identify Enterprise and Xella outstanding intercompany loans and settlement plan | Treasury / Risk Management | Day 1
Determine interim working capital needs for combined James Hardie | Treasury / Risk Management | Day 1
Assess global liquidity needs | Treasury / Risk Management | Day 1
Based upon cash flow and inter-company payments determine the optimal interest rat SWAP structure. | Treasury / Risk Management | Day 1
Determine requirements for debt instruments (covenants, interest rate swaps) and associated procedures | Treasury / Risk Management | Day 1
Identify and evaluate Enterprise procedures for letters of credit execution and monitoring, as needed | Treasury / Risk Management | Day 1
Bank Relationship and Account Management
Inventory Enterprise banking partners, accounts, and bank contacts | Treasury / Risk Management | Day 1
Document the Enterprise / James Hardie combines bank structure | Treasury / Risk Management | Day 1
Determine officers authorized to sign bank mandates | Treasury / Risk Management | Day 1
Determine associates authorized to process electronic payment and sign checks | Treasury / Risk Management | Day 1
Review the account analysis statements to determine what bank services are utilized. | Treasury / Risk Management | Day 1
Determine recent cash balances for all banks | Treasury / Risk Management | Day 1
Open new bank accounts to support new tax structure and replace existing bank accounts | Treasury / Risk Management | Day 1
Provide process change communication to banks providing services on Day One | Treasury / Risk Management | Day 1
After new boards are established, prepare bank resolutions authorized Enterprise / James Hardie officers | Treasury / Risk Management | Day 1
Update all bank mandates to authorize new bank officers. | Treasury / Risk Management | Day 60-120
Credit Cards
Determine if Enterprise issues Corporate credit cards / p-cards to employees. | Treasury / Risk Management | Day 1
Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company. | Treasury / Risk Management | Day 1
Review the process to interface credit card with ERP and other systems | Treasury / Risk Management | Day 1
Sign a new contract with the credit card company (incumbent or new) | Treasury / Risk Management | Day 1
Merchant Card Processing
Determine if Enterprise accepts credit card payments from customers | Treasury / Risk Management | Day 1
Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company. | Treasury / Risk Management | Day 1
Review the process to interface credit card with ERP and other systems | Treasury / Risk Management | Day 1
Sign a new contract with the credit card company (incumbent or new) | Treasury / Risk Management | Day 1
Cash Management
Identify and assume control of Enterprise cash globally | Treasury / Risk Management | Day 1
Determine combined James Hardie global cash forecasting and reporting processes | Treasury / Risk Management | Day 1
Determine daily cash concentration and positioning processes for combined James Hardie | Treasury / Risk Management | Day 1
Identify all Enterprise ACH debit / credit arrangements (tax, vendor payments) | Treasury / Risk Management | Day 1
Determine procedures and controls for executing electronic fund transfers (EFTs) | Treasury / Risk Management | Day 1
Foreign Exchange
Determine the non-functional currency balance sheet and cash flow hedge exposures. | Treasury / Risk Management | Day 1
Determine how the new intercompany structure will impact foreign exchange exposures.
Determine the best way to hedge the combined foreign exchange exposures | Treasury / Risk Management | Day 1
Insurance
Review and evaluate Enterprise exposures insured, limits and deductibles. | Treasury / Risk Management | Day 1
Obtain a list of current and former legal entities that need to be insured. If not in the United States, please identify the country incorporated. | Treasury / Risk Management | Day 1
Five year history of all open and closed insurance claims. If claims are open, please provide a status update. | Treasury / Risk Management | Day 1
Property - list of all locations detailing the address and values by locations (building value, inventory, contents, BI, CBI, and extra expense). | Treasury / Risk Management | Day 1
COPE information for all locations with values in excess of $1M | Treasury / Risk Management | Day 1
Property engineering, carrier inspection, and boiler/machinery inspection reports. | Treasury / Risk Management | Day 1
Description of interdependencies between locations. | Treasury / Risk Management | Day 1
Schedule of out-sourced manufacturing relationships including description, related sales/purchase volumes, and process criticality. | Treasury / Risk Management | Day 1
Schedule of certificates of insurance. | Treasury / Risk Management | Day 1
Projected international payroll and employee headcount by country. | Treasury / Risk Management | Day 1
Foreign sales to the US, sales from the US to other countries, and sales from international locations to other countries. | Treasury / Risk Management | Day 1
Schedule of import/export dollar values by product, geography, and type of vessel used to ship product | Treasury / Risk Management | Day 1
Equity Compensation
Information regarding new associates that will be granted equity options in the first quarter | Treasury / Risk Management | Day 1
Copy of all stock option agreements - PSA/U, RSA/U, SSR… | Treasury / Risk Management | Day 1
List of all employees receiving options, type of option being granted, and number of options / shares | Treasury / Risk Management | Day 1
Working Capital & Liquidity (NEW)
Assess working capital requirements for combined entity | Treasury / Risk Management | Day 1 |  |  |  |  | FP&A |  | High
Analyze cash flow and debt obligations to optimize liquidity | Treasury / Risk Management | Day 1 |  |  |  |  | FP&A |  | High
Monitor covenant compliance for combined debt structure | Treasury / Risk Management | Day 1 |  |  |  |  | Legal, FP&A |  | High
Develop 13-week cash flow forecast for combined entity | Treasury / Risk Management | Day 1 |  |  |  |  | FP&A |  | High
Debt & Capital Structure (NEW)
Refinance or restructure acquired company debt as needed | Treasury / Risk Management | Day 1 |  |  |  |  | Legal |  | High
Notify lenders and rating agencies of transaction close | Treasury / Risk Management | Day 1 |  |  |  |  | Investor Relations |  | High
Update capital structure analysis for combined entity | Treasury / Risk Management | Day 60-120 |  |  |  |  | FP&A |  | Medium
Optimize intercompany funding structure for tax efficiency | Treasury / Risk Management | Day 60-120 |  |  |  |  | Tax |  | Medium

## FP&A
Checklist - focus on Day 1
Financial Planning and Analysis |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Organization and Governance
Determine combined James Hardie FP&A department structure and accountability requirements for Day One | FP&A | Day 1
Train FP&A staff on Day One FP&A processes; provide communications on process changes as needed | FP&A | Day 1
Strategic Planning
Assess Fermacell strategic plan | FP&A | Day 1
Complete strategic planning session in June; includes combined James Hardie considerations | FP&A | Day 1
Budgeting and Planning
Understand Fermacell budgeting and forecasting processes | FP&A | Day 1
Develop combined FP&A Day One budgeting and forecasting processes; determine manual reporting requirements, as needed | FP&A | Day 1
Develop and obtain approval on combined James Hardie Day One forecast for interim/transition period | FP&A | Day 1
Develop integrated budget process and establish calendar for annual process given transaction close date; calendar to be provided prior to close | FP&A | Day 1
Identify combined FP&A budgeting and forecasting roles and responsibilities; communicate accordingly | FP&A | Day 1
Management Reporting
Identify Fermacell current Management Reporting package; determine all must-have reports | FP&A | Day 1
Rationalize James Hardie and Fermacell reports | FP&A | Day 1
Determine Combined James Hardie reporting requirements for Day One (reports, format, frequency, distribution); includes 'Flash' reporting process for P&L and Cash | FP&A | Day 1
Develop interim reporting calendar and plan for day 90 reporting requirements | FP&A | Day 1
Completed combined James Hardie revenue planning kick-off in Oct ‘14 to launch annual process | FP&A | Day 1
Compare and align management reporting data definitions (e.g. GL accounts and financial line items) | FP&A | Day 1
Communicate combined reporting requirements and processes to stakeholders | FP&A | Day 1
Understand Day One reporting requirements for debt financing | FP&A | Day 1
Performance Management Framework
Identify and review Fermacell current performance indicators/frameworks | FP&A | Day 1
Agree on Day One KPIs for internal reporting purposes with key stakeholders | FP&A | Day 1
Systems and Data
Create dimension in Hyperion to store baseline data | FP&A | Day 1
Assess Fermacell FP&A systems (e.g., Oracle) and determine level of entanglement with Xella systems | FP&A | Day 1
Assess potential risks / disruption to business due to changes to performance management systems | FP&A | Day 1
Determine Fermacell migration plan and data | FP&A | Day 1
Integration KPIs & Success Metrics (NEW)
Define financial integration success metrics | FP&A | Day 1 |  |  |  |  | PMO |  | High
Establish baseline measurements for operational efficiency KPIs | FP&A | Day 1 |  |  |  |  | Operations |  | High
Create integration dashboard for executive reporting | FP&A | Day 60-120 |  |  |  |  | PMO |  | High
Track customer satisfaction and retention through integration | FP&A | Day 60-120 |  |  |  |  | Sales |  | Medium
Monitor employee engagement metrics during transition | FP&A | Day 60-120 |  |  |  |  | HR |  | Medium
Talent & Organization (NEW)
Identify key finance talent for retention | FP&A | Day 1 |  |  |  |  | HR |  | High
Develop finance organization structure for combined entity | FP&A | Day 1 |  |  |  |  | HR |  | High
Plan retention bonuses for critical finance personnel | FP&A | Day 1 |  |  |  |  | HR, Compensation |  | High
Develop cross-training plan for combined finance team | FP&A | Day 60-120 |  |  |  |  | HR |  | Medium
Implement unified FP&A tools and reporting standards | FP&A | Year 1-2 |  |  |  |  | IT |  | Medium

## Baselining
Checklist - focus on Day 1
Baselining |  | Last updated: | 2026-01-29 13:23
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned finish date | Dependencies to/from other teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Identification of Finance Value Capture Opportunities
Conduct interviews with finance workstream leads to understand current finance processes | Baselining | Day 1
Identify Finance integration value capture targets | Baselining | Day 1
Develop detailed qualitative/quantitative business cases for Finance value capture initiatives | Baselining | Day 1
Review value capture initiatives with finance workstream leads | Baselining | Day 1
Develop a final validated list of value capture initiatives for the finance function | Baselining | Day 1
Review business cases and validate value capture targets with workstream leads | Baselining | Day 1
Planning for Value Capture
Develop detailed workplans for execution of each approved value driver initiative | Baselining | Day 1
Define metrics to track progress towards reaching value capture targets | Baselining | Day 1
Develop mechanism to report on value capture activities | Baselining | Day 1
Develop high level milestone plan showing value capture targets at various points along the integration timeline | Baselining | Day 1
Validation of value capture initiatives for other functions
Develop consolidated list of value capture initiatives identified by individual functions | Baselining | Day 1
Consolidate business cases developed by individual functions into master | Baselining | Day 1
Validate business cases for completeness and validate any assumptions made | Baselining | Day 1
Develop a consolidated value capture model across all functions | Baselining | Day 1
Validate consolidated value capture targets with cost synergies identified in deal model | Baselining | Day 1

## Executive Summary
FINANCE READINESS CHECKLIST - EXECUTIVE SUMMARY
M&A Integration Planning Tool
OVERVIEW
Purpose: | Comprehensive finance integration checklist for M&A transactions, covering Day 1 readiness through Year 1-2 integration
Use Case: | Acquisition of target company requiring TSA management, system integration, and finance function harmonization
FUNCTIONAL AREAS COVERED | # of Deliverables | Key Focus
1. TSA (Transition Services Agreement) | 32 | Service needs assessment, TSA schedules, governance, invoicing, EXIT PLANNING
2. Consolidation & External Reporting | 103 | Close processes, COA mapping, intercompany, SEC reporting, PRO FORMA MODELING, DATA GOVERNANCE
3. Operational Accounting | 93 | GL close, payroll, A/P, A/R, revenue recognition, cash mgmt, fixed assets, inventory
4. Internal Controls | 24 | SOX compliance, risk assessment, internal audit, ITGC, FRAUD RISK, ACCESS CONTROLS
5. Income Tax | 22 | Tax org, compliance, accounting methods, TRANSFER PRICING, INDIRECT TAX
6. Facilities & Indirect Sourcing | 27 | Real estate optimization, lease management, vendor rationalization
7. Treasury & Risk Management | 70 | Banking, cash mgmt, FX hedging, insurance, WORKING CAPITAL, COVENANT MONITORING
8. FP&A | 40 | Strategic planning, budgeting, reporting, KPIs, INTEGRATION METRICS, TALENT RETENTION
9. Baselining | 17 | Value capture identification, synergy validation, integration tracking
10. Cybersecurity & Data Privacy (NEW) | 30 | Cyber risk assessment, data privacy compliance, AI governance, security integration
11. ESG & Sustainability (NEW) | 22 | ESG due diligence, regulatory compliance, data collection, sustainability strategy
12. Integration Budget & Tracking (NEW) | 32 | Budget planning, stranded costs, synergy tracking, KPIs, change management
TOTAL DELIVERABLES | 512 | (+146 new deliverables added)
Day 60-120 | Integration milestones - SEC filings, process harmonization, system migrations
Year 1-2 | Full integration - consolidated systems, optimized processes, synergy realization
TRACKING DIMENSIONS
Each deliverable tracks:
• Sub-team / Functional Owner
• Related Milestone (Day 1 / Day 60-120 / Year 1-2)
• Applicability to Acquirer (JH) and Target (Fermacell)
• Responsibility (Name & Title)
• Planned Finish Date
• Dependencies to/from Other Teams
• Importance (High / Medium / Low)
• Status (Not Started / In Progress / Completed)
KEY STRENGTHS OF THIS CHECKLIST
✓ Comprehensive coverage of all finance sub-functions critical to M&A integration
✓ Phased approach (Day 1, Day 60-120, Year 1-2) enables prioritization
✓ Built-in dependency tracking across functional teams
✓ Importance rating allows resource allocation optimization
✓ Status tracking enables real-time progress monitoring
✓ Dual applicability flags for acquirer vs. target company tasks
HOW TO USE
1. Review each functional tab and customize deliverables to your transaction
2. Assign responsibilities and target dates for each deliverable
3. Update status weekly during integration execution
4. Use dependency fields to coordinate across workstreams
5. Filter by milestone to focus on immediate priorities
NEW SECTIONS ADDED (January 2026)
✓ Cybersecurity & Data Privacy | 30 deliverables covering cyber risk, data privacy, AI governance
✓ ESG & Sustainability | 22 deliverables for ESG due diligence, compliance, reporting
✓ Integration Budget & Tracking | 32 deliverables for budget, synergies, KPIs, change mgmt
ENHANCEMENTS TO EXISTING SECTIONS
• TSA: | +8 deliverables for exit planning, stranded costs, knowledge transfer
• Consolidation: | +12 deliverables for pro forma modeling, IFRS/GAAP, data governance
• Internal Controls: | +10 deliverables for ITGC, fraud risk, access controls, integration controls
• Income Tax: | +10 deliverables for transfer pricing, indirect tax, VAT/GST
• Treasury: | +10 deliverables for working capital, covenant monitoring, capital structure
• FP&A: | +12 deliverables for KPIs, success metrics, talent retention

## Cybersecurity & Data Privacy
Checklist - focus on Day 1
Cybersecurity & Data Privacy |  | Last updated: | 46051.5578
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Cybersecurity Risk Assessment
Conduct cybersecurity risk assessment of target's IT infrastructure | Cybersecurity | Day 1 |  |  |  |  | IT |  | High | Not started
Inventory all IT systems, applications, and data repositories | Cybersecurity | Day 1 |  |  |  |  | IT |  | High | Not started
Review target's data breach history and incident response procedures | Cybersecurity | Day 1 |  |  |  |  | Legal, IT |  | High | Not started
Assess network security controls and vulnerability management practices | Cybersecurity | Day 1 |  |  |  |  | IT |  | High | Not started
Review third-party vendor cybersecurity practices and contracts | Cybersecurity | Day 1 |  |  |  |  | Procurement, Legal |  | High | Not started
Identify cyber insurance coverage and gaps | Cybersecurity | Day 1 |  |  |  |  | Treasury, Legal |  | High | Not started
Develop IT system integration security plan | Cybersecurity | Day 1 |  |  |  |  | IT |  | High | Not started
Data Privacy Compliance
Inventory personal data collected by target (customers, employees, vendors) | Data Privacy | Day 1 |  |  |  |  | Legal, HR |  | High | Not started
Assess compliance with GDPR, CCPA, and other applicable privacy laws | Data Privacy | Day 1 |  |  |  |  | Legal |  | High | Not started
Review data processing agreements with third parties | Data Privacy | Day 1 |  |  |  |  | Legal, Procurement |  | Medium | Not started
Identify cross-border data transfer mechanisms and requirements | Data Privacy | Day 1 |  |  |  |  | Legal, IT |  | High | Not started
Review privacy policies and customer consent mechanisms | Data Privacy | Day 1 |  |  |  |  | Legal, Marketing |  | Medium | Not started
Assess data retention policies and practices | Data Privacy | Day 1 |  |  |  |  | Legal, IT |  | Medium | Not started
AI & Automation Governance
Inventory AI tools and automation systems used by target | AI Governance | Day 1 |  |  |  |  | IT, Operations |  | Medium | Not started
Assess AI-related risks (privacy, IP, bias, employment) | AI Governance | Day 1 |  |  |  |  | Legal, HR |  | Medium | Not started
Review AI vendor contracts and data usage terms | AI Governance | Day 1 |  |  |  |  | Legal, Procurement |  | Medium | Not started
Integration & Post-Close Security
Establish combined company data privacy policies | Cybersecurity | Day 60-120 |  |  |  |  | Legal, HR |  | High | Not started
Complete penetration testing of integrated systems | Cybersecurity | Day 60-120 |  |  |  |  | IT |  | High | Not started
Implement unified identity and access management (IAM) | Cybersecurity | Day 60-120 |  |  |  |  | IT, HR |  | High | Not started
Train employees on combined cybersecurity protocols | Cybersecurity | Day 60-120 |  |  |  |  | HR, IT |  | High | Not started
Migrate to unified security monitoring and incident response | Cybersecurity | Day 60-120 |  |  |  |  | IT |  | High | Not started
Update cyber insurance coverage for combined entity | Cybersecurity | Day 60-120 |  |  |  |  | Treasury, Legal |  | Medium | Not started
Long-term Security Integration
Consolidate security tools and platforms | Cybersecurity | Year 1-2 |  |  |  |  | IT |  | Medium | Not started
Implement unified data governance framework | Data Privacy | Year 1-2 |  |  |  |  | Legal, IT |  | Medium | Not started
Establish ongoing security audit and compliance program | Cybersecurity | Year 1-2 |  |  |  |  | Internal Audit, IT |  | Medium | Not started

## ESG & Sustainability
Checklist - focus on Day 1
ESG & Sustainability |  | Last updated: | 46051.5578
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
ESG Assessment & Due Diligence
Conduct ESG due diligence on target company | ESG | Day 1 |  |  |  |  | Legal, Operations |  | High | Not started
Identify material ESG risks and liabilities (environmental, social, governance) | ESG | Day 1 |  |  |  |  | Legal, Operations |  | High | Not started
Review environmental permits, compliance history, and remediation obligations | ESG | Day 1 |  |  |  |  | Legal, Facilities |  | High | Not started
Assess target's carbon footprint and emissions data | ESG | Day 1 |  |  |  |  | Operations |  | Medium | Not started
Review labor practices, health & safety records, and supply chain standards | ESG | Day 1 |  |  |  |  | HR, Operations |  | High | Not started
Regulatory Compliance
Identify applicable ESG reporting requirements (EU CSRD, SEC Climate, TCFD) | ESG | Day 1 |  |  |  |  | Legal, Finance |  | High | Not started
Assess combined company's ESG disclosure obligations | ESG | Day 1 |  |  |  |  | Legal, Investor Relations |  | High | Not started
Review target's existing ESG reports and ratings | ESG | Day 1 |  |  |  |  | Investor Relations |  | Medium | Not started
Data Collection & Reporting Integration
Inventory ESG data collection systems and processes at target | ESG | Day 60-120 |  |  |  |  | IT, Operations |  | Medium | Not started
Develop combined ESG data collection framework | ESG | Day 60-120 |  |  |  |  | Finance, Operations |  | High | Not started
Establish baseline ESG metrics for combined entity | ESG | Day 60-120 |  |  |  |  | Finance, Operations |  | High | Not started
Integrate ESG reporting into financial close process | ESG | Day 60-120 |  |  |  |  | Consolidation |  | Medium | Not started
Strategy & Long-term Integration
Develop combined company ESG strategy and targets | ESG | Year 1-2 |  |  |  |  | Strategy, Operations |  | High | Not started
Align sustainability policies and practices across combined entity | ESG | Year 1-2 |  |  |  |  | Operations, HR |  | Medium | Not started
Implement unified ESG reporting platform | ESG | Year 1-2 |  |  |  |  | IT, Finance |  | Medium | Not started
Establish ESG governance structure for combined company | ESG | Year 1-2 |  |  |  |  | Legal, Board |  | High | Not started
Communicate ESG commitments to stakeholders (investors, customers, employees) | ESG | Year 1-2 |  |  |  |  | Investor Relations, Comms |  | Medium | Not started
Obtain third-party ESG assurance/verification | ESG | Year 1-2 |  |  |  |  | External Audit |  | Medium | Not started

## Integration Budget & Tracking
Checklist - focus on Day 1
Integration Budget & Tracking |  | Last updated: | 46051.5578
Drop-down menus |  | Related Milestone | Applicable to JH | Applicable to F |  |  |  |  | Importance | Status
|  | Day 1 | Yes | Yes |  |  |  |  | High | Not started
|  | Day 60-120 | No | No |  |  |  |  | Medium | In progress - on track
|  | Year 1-2 | [6 empty] | Low | In progress - delayed
Completed
Deliverable | Sub team | Related Milestone | Applicable to James Hardie? | Applicable to Fermacell? | Responsibility | Planned Finish Date | Dependencies to/from Other Teams | Comment on dependencies | Importance | Status
Item - e.g., Alignment of reporting arrangements |  | e.g., Day 1 | Yes / No | Yes / No | Name & Title | Date | Business lines |  | E.g., High | E.g., Not started
Integration Budget Planning
Develop comprehensive integration budget by workstream | Integration Budget | Day 1 |  |  |  |  | All Workstreams |  | High | Not started
Identify one-time integration costs vs. ongoing run-rate costs | Integration Budget | Day 1 |  |  |  |  | FP&A |  | High | Not started
Establish integration cost tracking and reporting cadence | Integration Budget | Day 1 |  |  |  |  | FP&A, PMO |  | High | Not started
Define cost approval thresholds and governance process | Integration Budget | Day 1 |  |  |  |  | Finance Leadership |  | High | Not started
Stranded Costs Management
Identify potential stranded costs from TSA exits | Stranded Costs | Day 1 |  |  |  |  | TSA, FP&A |  | High | Not started
Develop stranded cost mitigation plan | Stranded Costs | Day 1 |  |  |  |  | All Functions |  | High | Not started
Track stranded cost run-off timeline | Stranded Costs | Day 60-120 |  |  |  |  | FP&A |  | Medium | Not started
Synergy Tracking
Develop synergy tracking model aligned with deal model assumptions | Synergy Tracking | Day 1 |  |  |  |  | FP&A, Corp Dev |  | High | Not started
Define synergy categories (cost, revenue, capital) | Synergy Tracking | Day 1 |  |  |  |  | FP&A |  | High | Not started
Establish synergy measurement methodology and baseline | Synergy Tracking | Day 1 |  |  |  |  | FP&A |  | High | Not started
Create synergy tracking dashboard for leadership reporting | Synergy Tracking | Day 60-120 |  |  |  |  | FP&A |  | High | Not started
Implement monthly synergy realization reporting | Synergy Tracking | Day 60-120 |  |  |  |  | FP&A |  | High | Not started
Reconcile synergy actuals to deal model projections | Synergy Tracking | Day 60-120 |  |  |  |  | FP&A, Corp Dev |  | High | Not started
Integration KPIs & Success Metrics
Define integration success metrics and KPIs | KPIs | Day 1 |  |  |  |  | PMO, FP&A |  | High | Not started
Establish baseline measurements for all KPIs | KPIs | Day 1 |  |  |  |  | All Workstreams |  | High | Not started
Implement integration scorecard for steering committee | KPIs | Day 60-120 |  |  |  |  | PMO |  | High | Not started
Track customer satisfaction through integration | KPIs | Day 60-120 |  |  |  |  | Sales, Operations |  | Medium | Not started
Track employee engagement/retention through integration | KPIs | Day 60-120 |  |  |  |  | HR |  | Medium | Not started
Communication & Change Management
Develop integration communication plan (internal and external) | Change Mgmt | Day 1 |  |  |  |  | Comms, HR |  | High | Not started
Establish integration governance structure (PMO, Steering Committee) | Change Mgmt | Day 1 |  |  |  |  | Executive Leadership |  | High | Not started
Define escalation paths and decision-making protocols | Change Mgmt | Day 1 |  |  |  |  | PMO |  | High | Not started
Implement regular town halls and integration updates | Change Mgmt | Day 60-120 |  |  |  |  | Comms, HR |  | Medium | Not started
Develop change management training for managers | Change Mgmt | Day 60-120 |  |  |  |  | HR |  | Medium | Not started
Post-Integration Review
Conduct integration lessons learned sessions | Post-Integration | Year 1-2 |  |  |  |  | All Workstreams |  | Medium | Not started
Document integration playbook for future transactions | Post-Integration | Year 1-2 |  |  |  |  | PMO, Corp Dev |  | Medium | Not started
Final synergy realization assessment vs. deal model | Post-Integration | Year 1-2 |  |  |  |  | FP&A, Corp Dev |  | High | Not started