## Master Checklist
Item_ID | PRD_L1_Domain | Workstream_L2 | Section_L3 | Deliverable | Sub_Team | Phase | Importance | Status | Dependencies | TSA_Relevant | Day1_Critical
FRC-0001 | TSA / Deal Structure | TSA | Assessment of Service needs | Review existing TSA schedules developed by Xella | TSA | Day 1 |  |  |  | Yes
FRC-0002 | TSA / Deal Structure | TSA | Assessment of Service needs | Develop a TSA tracker listing out for each TSA, the scope of services, related function, service fees, duration, location, TSA owners etc. | TSA | Day 1 |  |  |  | Yes
FRC-0003 | TSA / Deal Structure | TSA | Assessment of Service needs | Conduct interviews with each function at Fermacell to identify services currently provided by Xella to Fermacell | TSA | Day 1 |  |  |  | Yes
FRC-0004 | TSA / Deal Structure | TSA | Assessment of Service needs | Determine services provided by Xella teams that are not transferring with the deal | TSA | Day 1 |  |  |  | Yes
FRC-0005 | TSA / Deal Structure | TSA | Assessment of Service needs | Determine services provided by Xella to Fermacell that could be provided in-house by Fermacell | TSA | Day 1 |  |  |  | Yes
FRC-0006 | TSA / Deal Structure | TSA | Assessment of Service needs | Conduct interviews with James Hardie functions to determine services that James Hardie can provide to replace those provided by Xella | TSA | Day 1 |  |  |  | Yes
FRC-0007 | TSA / Deal Structure | TSA | Assessment of Service needs | Develop list if services for which Transition Services Agreements will be needed | TSA | Day 1 |  |  |  | Yes
FRC-0008 | TSA / Deal Structure | TSA | Assessment of Service needs | Identify gaps between services in the TSA schedule provided by Xella and those identified through interviews with functional leads from James Hardie and Fermacell | TSA | Day 1 |  |  |  | Yes
FRC-0009 | TSA / Deal Structure | TSA | Assessment of Service needs | Validate the services for which support will be required through TSAs with each functional lead at Fermacell, James Hardie, and Xella | TSA | Day 1 |  |  |  | Yes
FRC-0010 | TSA / Deal Structure | TSA | Schedule of TSA services | Conduct interviews with Fermacell functional leads to develop detailed scope of services to be provided under each TSA | TSA | Day 1 |  |  |  | Yes
FRC-0011 | TSA / Deal Structure | TSA | Schedule of TSA services | Identify locations at which TSAs are needed as well as TSA duration | TSA | Day 1 |  |  |  | Yes
FRC-0012 | TSA / Deal Structure | TSA | Schedule of TSA services | Legal team to draft TSA schedules for each service that Xella will need to provide, if TSA schedule does not already exist | TSA | Day 1 |  |  |  | Yes
FRC-0013 | TSA / Deal Structure | TSA | Schedule of TSA services | Legal team to modify existing TSA schedules based on feedback from functional leads from James Hardie and Fermacell functional leads | TSA | Day 1 |  |  |  | Yes
FRC-0014 | TSA / Deal Structure | TSA | Schedule of TSA services | Discuss updated TSA schedule with Xella through executive steering committee meetings | TSA | Day 1 |  |  |  | Yes
FRC-0015 | TSA / Deal Structure | TSA | Schedule of TSA services | Modify TSA schedules as needed based on feedback from functional leads | TSA | Day 1 |  |  |  | Yes
FRC-0016 | TSA / Deal Structure | TSA | Schedule of TSA services | Review modified TSA schedules with functional leads from James Hardie, Fermacell and Xella and get sign off from all parties | TSA | Day 1 |  |  |  | Yes
FRC-0017 | TSA / Deal Structure | TSA | Schedule of TSA services | Draft final (execution version) of TSA schedule to be signed at deal close | TSA | Day 1 |  |  |  | Yes
FRC-0018 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Identify TSA owners from Xella (Service Provider) and James Hardie/Fermacell (Service Recipient) | TSA | Day 1 |  |  |  | Yes
FRC-0019 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Develop a TSA governance process based on terms in the Form of Transition Services | TSA | Day 1 |  |  |  | Yes
FRC-0020 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Review the governance process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties | TSA | Day 1 |  |  |  | Yes
FRC-0021 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Develop a process to calculate TSA fees on a monthly basis and to generate invoices | TSA | Day 1 |  |  |  | Yes
FRC-0022 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Review the invoicing process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties | TSA | Day 1 |  |  |  | Yes
FRC-0023 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Define TSA exit criteria and transition milestones for each service | TSA | Day 1 |  |  |  | Yes
FRC-0024 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Identify stranded costs associated with TSA exits | TSA | Day 1 | High |  | FP&A | Yes | Yes
FRC-0025 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Develop TSA exit readiness assessment process | TSA | Day 60-120 |  |  |  | Yes
FRC-0026 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Create TSA wind-down communication plan with seller | TSA | Day 60-120 |  |  | Legal | Yes
FRC-0027 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Track TSA cost vs. internal capability build costs | TSA | Day 60-120 | Medium |  | FP&A | Yes
FRC-0028 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Execute TSA termination notices per contractual requirements | TSA | Year 1-2 | High |  | Legal | Yes
FRC-0029 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Complete knowledge transfer from TSA providers | TSA | Year 1-2 | High |  | All Functions | Yes
FRC-0030 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Understand current James Hardie and Fermacell org structures including roles and responsibilities | Consolidation & Ext Reporting | Day 1
FRC-0031 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Identify key contacts/counterparts across the regions | Consolidation & Ext Reporting | Day 1
FRC-0032 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Gather and share org chart, chart of accounts, entity listing, currencies, etc. between Fermacell and James Hardie | Consolidation & Ext Reporting | Day 1
FRC-0033 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Obtain policies and procedures on monthly close and close schedule with cut-offs and timing | Consolidation & Ext Reporting | Day 1
FRC-0034 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Establish the NewCo financial close calendar | Consolidation & Ext Reporting | Day 1
FRC-0035 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Review functional currencie of all Fermacells entities and address changes, as needed | Consolidation & Ext Reporting | Day 1
FRC-0036 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Develop task list for monthly consolidation combined company close | Consolidation & Ext Reporting | Day 1
FRC-0037 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Develop contingency plan for potential mid-month close(i.e., stub period) dependent on anti-trust approvals | Consolidation & Ext Reporting | Day 1
FRC-0038 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Review task list for monthly / quarterly reporting | Consolidation & Ext Reporting | Day 1
FRC-0039 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Document trial balance submission timing to align with Fermacell entities | Consolidation & Ext Reporting | Day 1
FRC-0040 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Test upload/input format file | Consolidation & Ext Reporting | Day 1
FRC-0041 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Perform trial balances submission in consolidation system | Consolidation & Ext Reporting | Day 1
FRC-0042 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand the IT landscape for consolidation and reporting structures by product line and geographical area | Consolidation & Ext Reporting | Day 1
FRC-0043 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand James Hardie / Fermacell consolidation procedures (upload, journal entries, etc.) | Consolidation & Ext Reporting | Day 1
FRC-0044 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand Fermacell account structure (custom dimensions, cost center, etc.) | Consolidation & Ext Reporting | Day 1
FRC-0045 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Establish future state legal entity and reporting structure for combined company | Consolidation & Ext Reporting
FRC-0046 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Create org structure/codes in consolidation system based on legal/tax structure | Consolidation & Ext Reporting | Day 1
FRC-0047 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Review Fermacell chart of accounts and identifes differences | Consolidation & Ext Reporting | Day 1
FRC-0048 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Develop the approach to managing multiple chart of accounts | Consolidation & Ext Reporting | Day 1
FRC-0049 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Determine approach for chart of account mapping between Fermacell/James Hardie (Fermacell Oracle to James Hardie Oracle, Fermacell Oracle to James Hardie Hyperion) | Consolidation & Ext Reporting | Day 1
FRC-0050 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Map Fermacell chart of accounts to James Hardie chart of accounts | Consolidation & Ext Reporting | Day 1
FRC-0051 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Identify new accounts to be created,closed or renamed | Consolidation & Ext Reporting | Day 1
FRC-0052 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Identify I/C accounts to assign intercompany partner | Consolidation & Ext Reporting | Day 1
FRC-0053 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Map intercompany accounts to intercompany partner | Consolidation & Ext Reporting | Day 1
FRC-0054 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Review preliminary mapping with technical accounting and flag accounts requiring attention | Consolidation & Ext Reporting | Day 1
FRC-0055 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Communicate with reporting FP&A teams to understand reporting requirements/decisions | Consolidation & Ext Reporting | Day 1
FRC-0056 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Consider impact of further system implementation on mapping (e.g. Hyperion redesign) | Consolidation & Ext Reporting | Day 1
FRC-0057 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Build of FDM Mapping Tables | Consolidation & Ext Reporting | Day 1
FRC-0058 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Test and validate mapping tables | Consolidation & Ext Reporting | Day 1
FRC-0059 | Finance & Accounting | Consolidation & Ext. Repo | Training and access | Provide system access, as necessary | Consolidation & Ext Reporting | Day 1
FRC-0060 | Finance & Accounting | Consolidation & Ext. Repo | Training and access | Train identified employees on system applications | Consolidation & Ext Reporting | Day 1
FRC-0061 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Perform inventory of I/C relationships | Consolidation & Ext Reporting | Day 1
FRC-0062 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Assess integration impact on current and expected intercompany transactions | Consolidation & Ext Reporting | Day 1
FRC-0063 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.) | Consolidation & Ext Reporting | Day 1
FRC-0064 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Understand multi-arrangements transactions and assess materiality, if any | Consolidation & Ext Reporting | Day 1
FRC-0065 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Assess current process for capturing intercompany activity and assess applicability to current business requirements | Consolidation & Ext Reporting | Day 1
FRC-0066 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell | Consolidation & Ext Reporting | Day 1
FRC-0067 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Create new intercompany trading partners and accounts | Consolidation & Ext Reporting | Day 1
FRC-0068 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Obtain listing of purchase accounting adjustments based on draft and final valuation reports | Consolidation & Ext Reporting | Day 1
FRC-0069 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Determine approach and confirm push-down level of purchase accounting entries (entity, country, regional, corporate) | Consolidation & Ext Reporting | Day 1
FRC-0070 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Confirm feasibility and document push-down approach | Consolidation & Ext Reporting | Day 1
FRC-0071 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Collect and review all policies, standards and procedures | Consolidation & Ext Reporting | Day 1
FRC-0072 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Perform policy gap analysis to understand accounting difference between Fermacell and James Hardie | Consolidation & Ext Reporting | Day 1
FRC-0073 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Assess materiality of difference in accounting policy | Consolidation & Ext Reporting | Day 1
FRC-0074 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Understand new accounting policies required as result of the merger | Consolidation & Ext Reporting | Day 1
FRC-0075 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Prioritize accounting policies to be developed requiring Day 1 alignment | Consolidation & Ext Reporting | Day 1
FRC-0076 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Develop revised or common policies and procedures | Consolidation & Ext Reporting | Day 1
FRC-0077 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Obtain approval from policy steering committee | Consolidation & Ext Reporting | Day 1
FRC-0078 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Train employees and implent policies | Consolidation & Ext Reporting
FRC-0079 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Identify main differences between James Hardie and Fermacell disclosures | Consolidation & Ext Reporting | Day 1
FRC-0080 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Identify new accounts to be created to support SEC disclosures/accounts roll forward | Consolidation & Ext Reporting | Day 1
FRC-0081 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Prepare historical combined company financial statements and key performance indicators | Consolidation & Ext Reporting | Day 1
FRC-0082 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop plan to produce 8-K reporting required Day 4 post-close and identify data requirements | Consolidation & Ext Reporting | Day 1
FRC-0083 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop plan to produce Offering Memorandum (OM) post-close and identify data requirements | Consolidation & Ext Reporting | Day 1
FRC-0084 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Agree upon NewCo financial statement reporting requirements | Consolidation & Ext Reporting | Day 1
FRC-0085 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Determine James Hardie and Fermacell’s Day 1 reporting segments | Consolidation & Ext Reporting | Day 1
FRC-0086 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft outline of NewCo interim financial statements for review | Consolidation & Ext Reporting | Day 1
FRC-0087 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft purchase accounting footnote | Consolidation & Ext Reporting | Day 1
FRC-0088 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft pro forma financial statements | Consolidation & Ext Reporting | Day 1
FRC-0089 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop merger related disclosures (e.g., stock compensation) | Consolidation & Ext Reporting | Day 1
FRC-0090 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Submit Offering Memorandum (OM) post- Day 1 | Consolidation & Ext Reporting | Day 1
FRC-0091 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Submit amended 8-KA with financials within 75 days post-close | Consolidation & Ext Reporting | Day 60-120
FRC-0092 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Define post-Day 1data requirements to integrated reporting | Consolidation & Ext Reporting | Day 60-120
FRC-0093 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Understand current system processes to perform statutory reports | Consolidation & Ext Reporting | Day 1
FRC-0094 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Inventory all reporting requirements and status of each | Consolidation & Ext Reporting | Day 1
FRC-0095 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Update inventory based upon local legal merger | Consolidation & Ext Reporting | Day 1
FRC-0096 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Determine valuation requirements for local tax mergers | Consolidation & Ext Reporting | Day 1
FRC-0097 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Engage appraiser, as necessary | Consolidation & Ext Reporting | Day 1
FRC-0098 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Structure opening balance sheet accounting based upon local legal merger plan | Consolidation & Ext Reporting | Day 1
FRC-0099 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Link transaction accounting to local legal merger plan | Consolidation & Ext Reporting | Day 1
FRC-0100 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Obtain both company close packages and identify unique key performance indicators | Consolidation & Ext Reporting | Day 1
FRC-0101 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Understand current reporting responsibilities, systems and processes | Consolidation & Ext Reporting | Day 1
FRC-0102 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Agree upon the combined company key performance indicators for reporting purposes | Consolidation & Ext Reporting | Day 1
FRC-0103 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Validate availability of information within accounting close function | Consolidation & Ext Reporting | Day 1
FRC-0104 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Review key performance indicators and management reporting package with investor relations | Consolidation & Ext Reporting | Day 1
FRC-0105 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Design the combined company interim close packages | Consolidation & Ext Reporting | Day 1
FRC-0106 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Agree upon reporting requirements and key stakeholders (including credit agencies and other reporting needs) | Consolidation & Ext Reporting | Day 1
FRC-0107 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Train personnel on financial information available and discussion/narrative requirements | Consolidation & Ext Reporting | Day 1
FRC-0108 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Review and compare James Hardie and Fermacell cash flow statement models and identify gaps | Consolidation & Ext Reporting | Day 1
FRC-0109 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Develop process to produce combined statement of cash flows | Consolidation & Ext Reporting | Day 1
FRC-0110 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Prepare combined cash flow statement for SEC filing | Consolidation & Ext Reporting | Day 1
FRC-0111 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Develop pro forma financial model for combined entity | Consolidation & Ext Reporting | Day 1 | High |  | FP&A |  | Yes
FRC-0112 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Create model of expected revenue synergies and cost savings | Consolidation & Ext Reporting | Day 1 | High |  | FP&A, Corp Dev |  | Yes
FRC-0113 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Establish data retention protocols for acquired company financial data | Consolidation & Ext Reporting | Day 1 | High |  | IT, Legal |  | Yes
FRC-0114 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Identify IFRS vs. GAAP accounting differences between entities | Consolidation & Ext Reporting | Day 1 | High |  | Technical Accounting |  | Yes
FRC-0115 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Develop IFRS/GAAP reconciliation procedures | Consolidation & Ext Reporting | Day 1 | High |  | Technical Accounting |  | Yes
FRC-0116 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Determine reporting framework for combined entity | Consolidation & Ext Reporting | Day 1 | High |  | Legal, Technical Accounting |  | Yes
FRC-0117 | Finance & Accounting | Consolidation & Ext. Repo | Data Governance (NEW) | Audit acquired company's financial data quality and completeness | Consolidation & Ext Reporting | Day 1 | High |  | IT, Internal Audit |  | Yes
FRC-0118 | Finance & Accounting | Consolidation & Ext. Repo | Data Governance (NEW) | Establish combined company data governance framework | Consolidation & Ext Reporting | Day 60-120 | Medium |  | IT, Finance
FRC-0119 | Finance & Accounting | Consolidation & Ext. Repo | Data Governance (NEW) | Define master data management approach for combined entity | Consolidation & Ext Reporting | Day 60-120 | Medium |  | IT
FRC-0120 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Obtain policies and procedures on monthly close and close schedule with cut-offs and timing | Operational Accounting | Day 1 |  | Not started
FRC-0121 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Identify and manage differences in chart of accounts | Operational Accounting | Day 1 |  | Not started
FRC-0122 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Develop the approach to managing multiple chart of accounts | Operational Accounting | Day 1 |  | Not started
FRC-0123 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Identify tools needed to perform the monthly consolidation | Operational Accounting | Day 1 |  | Not started
FRC-0124 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Establish the interim combined company financial close calendar | Operational Accounting | Day 1 |  | Not started
FRC-0125 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Develop contingency plan based upon different deal close date scenarios | Operational Accounting | Day 1 |  | Not started
FRC-0126 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Assess opportunity for close process improvement | Operational Accounting | Day 1
FRC-0127 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Adjust the close processes incrementally | Operational Accounting | Day 60-120
FRC-0128 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Align the accounting close with strategic priorities | Operational Accounting | Day 60-120
FRC-0129 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Establish improved NewCo financial close calendar | Operational Accounting | Day 60-120 |  | Not started
FRC-0130 | Finance & Accounting | Operational Accounting | Payroll | Assess current state processes | Operational Accounting | Day 1 |  | Not started
FRC-0131 | Finance & Accounting | Operational Accounting | Payroll | Confirm listing of employees census, geographical location and legal entity structuring | Operational Accounting | Day 1
FRC-0132 | Finance & Accounting | Operational Accounting | Payroll | Plan enrollment procedures for Day 1 acquired employees | Operational Accounting | Day 1 |  | Not started
FRC-0133 | Finance & Accounting | Operational Accounting | Payroll | Determine systems required to manage Fermacell payroll functions of Day 1 | Operational Accounting | Day 1 |  | Not started
FRC-0134 | Finance & Accounting | Operational Accounting | Payroll | Develop interim operating model for Day 1 | Operational Accounting | Day 1 |  | Not started
FRC-0135 | Finance & Accounting | Operational Accounting | Payroll | Understand downstream benefit accounting impacts based on HR decisions | Operational Accounting | Day 1 |  | Not started
FRC-0136 | Finance & Accounting | Operational Accounting | Payroll | Migrate payroll data sets to integrated system | Operational Accounting | Day 60-120 |  | Not started
FRC-0137 | Finance & Accounting | Operational Accounting | Payroll | Establish fully integrate payroll processing function | Operational Accounting | Year 1-2 |  | Not started
FRC-0138 | Finance & Accounting | Operational Accounting | Accounts payable | Understand current A/P processing (domestic and international) | Operational Accounting | Day 1 |  | Not started
FRC-0139 | Finance & Accounting | Operational Accounting | Accounts payable | Identify responsibility for payables processing for Day 1 | Operational Accounting | Day 1 |  | Not started
FRC-0140 | Finance & Accounting | Operational Accounting | Accounts payable | Identify opportunities to consolidate efforts for accounts payable (domestic and international) | Operational Accounting | Day 60-120 |  | Not started
FRC-0141 | Finance & Accounting | Operational Accounting | Accounts payable | Standardize approach for timing of payments (i.e., frequency of check cuts and discounts) | Operational Accounting | Day 60-120 |  | Not started
FRC-0142 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Identify responsibility for processing time and expenses | Operational Accounting | Day 1 |  | Not started
FRC-0143 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Determine and develop approach to time and expense reimbursement (e.g., through direct deposit, with normal paycheck, or separate run) | Operational Accounting | Day 1 |  | Not started
FRC-0144 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Communicate travel and expense policies and procedures corporate wide | Operational Accounting | Day 1 |  | Not started
FRC-0145 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Implement T&E control framework/policy | Operational Accounting | Day 60-120 |  | Not started
FRC-0146 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Develop the combined invoicing process under NewCo | Operational Accounting | Day 1 |  | Not started
FRC-0147 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Determine intracompany invoicing currency | Operational Accounting | Day 1 |  | Not started
FRC-0148 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Generate an update letter for customers with NewCo name change. Coordinate with company announcement. | Operational Accounting | Day 1 |  | Not started
FRC-0149 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Develop communication plan for sales team for invoicing practices | Operational Accounting | Day 1 |  | Not started
FRC-0150 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Determine updated sales tax requirements | Operational Accounting | Day 1 |  | Not started
FRC-0151 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Define returns and billing adjustment policies | Operational Accounting | Day 1 |  | Not started
FRC-0152 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Understand differences in credit policies | Operational Accounting | Day 1 |  | Not started
FRC-0153 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Review credit files and evaluate major creditors for any new exposures | Operational Accounting | Day 1 |  | Not started
FRC-0154 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Evaluate credit limits for common customers and determine the combined company credit limit | Operational Accounting | Day 1 |  | Not started
FRC-0155 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Standardize the credit approval and documentation process | Operational Accounting | Day 1 |  | Not started
FRC-0156 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Identify differences in "account overdue" definition and standardize | Operational Accounting | Day 1 |  | Not started
FRC-0157 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Identify differences in the collection process and standardize | Operational Accounting | Day 1 |  | Not started
FRC-0158 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Consolidate credit collections agents | Operational Accounting | Day 1 |  | Not started
FRC-0159 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Establish a consistent write off policy | Operational Accounting | Day 1 |  | Not started
FRC-0160 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify revenue recognition methodology differences between companies and determine Day 1 policy | Operational Accounting | Day 1 |  | Not started
FRC-0161 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Determine how any revenue recognition methodology changes impact the current sales and contracting process | Operational Accounting | Day 1 |  | Not started
FRC-0162 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Update standard contracts, as necessary | Operational Accounting | Day 1 |  | Not started
FRC-0163 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Determine combined company ales model and cummuncate with field sales team | Operational Accounting | Day 1 |  | Not started
FRC-0164 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify any issues between the proposed sales model to the proposed revenue recognition methodology | Operational Accounting | Day 1 |  | Not started
FRC-0165 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify any contracting conflicts caused by the proposed sales model | Operational Accounting | Day 1 |  | Not started
FRC-0166 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Work with Sales Management to revise sales models and methodologies for revenue recognition and contracting | Operational Accounting | Day 1 |  | Not started
FRC-0167 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Train and implement amended receivable policies | Operational Accounting | Day 1 |  | Not started
FRC-0168 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify opportunities to consolidate efforts for accounts receivable (domestic and international) | Operational Accounting | Day 60-120 |  | Not started
FRC-0169 | Finance & Accounting | Operational Accounting | Cash management | Perform bank account reconciliation and consolidation | Operational Accounting | Day 1 |  | Not started
FRC-0170 | Finance & Accounting | Operational Accounting | Cash management | Update and finalize Day 1 banking requirements | Operational Accounting | Day 1 |  | Not started
FRC-0171 | Finance & Accounting | Operational Accounting | Cash management | Ensure Day 1 funding and purchase accounting | Operational Accounting | Day 1
FRC-0172 | Finance & Accounting | Operational Accounting | Cash management | Identify long-term cash management responsibility (signing, bank notification) and implement cash management functionality (bank, auto or manual) | Operational Accounting | Day 1 |  | Not started
FRC-0173 | Finance & Accounting | Operational Accounting | Cash management | Identify any 3rd party debt and payment requirements | Operational Accounting | Day 1 |  | Not started
FRC-0174 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Identify IT requirements for Day 1 wire transfers and implement (auto or manual) | Operational Accounting | Day 1 |  | Not started
FRC-0175 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Update and communicate new signature process | Operational Accounting | Day 1 |  | Not started
FRC-0176 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Identify required vendor wire transfers and confirm set up | Operational Accounting | Day 1 |  | Not started
FRC-0177 | Finance & Accounting | Operational Accounting | Intercompany elimination | Perform inventory of I/C relationships | Operational Accounting | Day 1
FRC-0178 | Finance & Accounting | Operational Accounting | Intercompany elimination | Assess integration impact on current and expected intercompany transactions | Operational Accounting | Day 1
FRC-0179 | Finance & Accounting | Operational Accounting | Intercompany elimination | Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.) | Operational Accounting | Day 1
FRC-0180 | Finance & Accounting | Operational Accounting | Intercompany elimination | Understand multi-arrangements transactions and assess materiality, if any | Operational Accounting | Day 1
FRC-0181 | Finance & Accounting | Operational Accounting | Intercompany elimination | Assess current process for capturing intercompany activity and assess applicability to current business requirements | Operational Accounting | Day 1
FRC-0182 | Finance & Accounting | Operational Accounting | Intercompany elimination | Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell | Operational Accounting | Day 1
FRC-0183 | Finance & Accounting | Operational Accounting | Intercompany elimination | Create new intercompany trading partners and accounts | Operational Accounting | Day 1
FRC-0184 | Finance & Accounting | Operational Accounting | Fixed assets | Assess current but not yet started projects | Operational Accounting | Day 1 |  | Not started
FRC-0185 | Finance & Accounting | Operational Accounting | Fixed assets | Determine if a fixed asset inventory is required and implement if necessary (coordinate with IT for IT hardware) | Operational Accounting | Day 1 |  | Not started
FRC-0186 | Finance & Accounting | Operational Accounting | Fixed assets | Develop approach to managing assets that will be disposed of on Day 1, if applicable | Operational Accounting | Day 1 |  | Not started
FRC-0187 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize procedures for asset retirement and disposal | Operational Accounting | Day 1 |  | Not started
FRC-0188 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize capitalization policies and procedures | Operational Accounting | Day 1 |  | Not started
FRC-0189 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize depreciation methods | Operational Accounting | Day 1 |  | Not started
FRC-0190 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Identify all projects and initiatives (capex and other) in progress or about to be launched and review with respect to NewCo structure and objectives. Rationalize if required | Operational Accounting | Day 1 |  | Not started
FRC-0191 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Identify critical projects and launches that need to managed through the transition to minimize risk of failure | Operational Accounting | Day 1 |  | Not started
FRC-0192 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Review all current major projects for compliance with delivery dates | Operational Accounting | Day 1 |  | Not started
FRC-0193 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Review all current major projects for cost status versus budget and forecast | Operational Accounting | Day 1 |  | Not started
FRC-0194 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Ensure project reporting systems provide adequate management information | Operational Accounting | Day 1 |  | Not started
FRC-0195 | Finance & Accounting | Operational Accounting | Inventory | Assess current inventory policies and processes (reserves, returns, costing) | Operational Accounting | Day 1 |  | Not started
FRC-0196 | Finance & Accounting | Operational Accounting | Inventory | Align material differences in accounting policy | Operational Accounting | Day 1 |  | Not started
FRC-0197 | Finance & Accounting | Operational Accounting | Inventory | Conduct inventory valuations, as required | Operational Accounting | Day 1
FRC-0198 | Finance & Accounting | Operational Accounting | Contracts | Review any exclusive purchasing agreements or preferred supplier for conflicts | Operational Accounting | Day 1
FRC-0199 | Finance & Accounting | Operational Accounting | Contracts | Review payment terms and determine what actions, if any, need to take place | Operational Accounting | Day 1
FRC-0200 | Finance & Accounting | Internal Controls | Internal Audit | Assist management by evaluating the design and effectiveness of critical operating controls and estblish remediation strategies. | Internal Audit | Day 1
FRC-0201 | Finance & Accounting | Internal Controls | Internal Audit | Develop an understanding of Fermacell's SOX and IA programs and prior year SOX/IA results. | Internal Audit | Day 1
FRC-0202 | Finance & Accounting | Internal Controls | Internal Audit | Plan 2018 Fermacell controls testing strategy to support 2018 EY substantive audit activities | Internal Audit | Day 1
FRC-0203 | Finance & Accounting | Internal Controls | Internal Audit | Assist management with designing and implementing acquisition transaction controls (e.g., FCR, Treasury, Tax) | Internal Audit | Day 1
FRC-0204 | Finance & Accounting | Internal Controls | Internal Audit | Understand requirements defined in TSA and perform a risk evaluation. | Internal Audit | Day 1 |  |  |  | Yes
FRC-0205 | Finance & Accounting | Internal Controls | Internal Audit | Determine IA staffing/cosource needs including longer term audit department structure and short term needs for SOX requirements. | Internal Audit | Day 1
FRC-0206 | Finance & Accounting | Internal Controls | Internal Audit | Conduct Fermacell Risk Assessment | Internal Audit | Day 30
FRC-0207 | Finance & Accounting | Internal Controls | Internal Audit | Execute 2018 Fermacell controls testing, to support EY substantive audit activities. | Internal Audit | Day 1
FRC-0208 | Finance & Accounting | Internal Controls | Internal Audit | Conduct New Co. risk assessment while leveraging Fermacell risk assessment results. | Internal Audit | Day 1
FRC-0209 | Finance & Accounting | Internal Controls | Internal Audit | Define the future SOX plan for New Co. | Internal Audit | Day 1
FRC-0210 | Finance & Accounting | Internal Controls | Internal Audit | Refine existing 302 certification plan | Internal Audit | Day 1
FRC-0211 | Finance & Accounting | Internal Controls | Internal Audit | Conduct a TSA compliance audit for high risk areas. | Internal Audit | Day 1 |  |  |  | Yes
FRC-0212 | Finance & Accounting | Internal Controls | Internal Audit | Execute audits supporting regulatory compliance including EU Safe Harbor and Conflict Minerals) | Internal Audit | Day 1
FRC-0213 | Finance & Accounting | Internal Controls | Internal Audit | Evaluate and purchase an IA/SOX document retention tool. | Internal Audit | Day 1
FRC-0214 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Design controls for new intercompany transactions | Internal Audit | Day 1 | High |  | Operational Accounting |  | Yes
FRC-0215 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Assess IT General Controls (ITGC) for acquired systems | Internal Audit | Day 1 | High |  | IT |  | Yes
FRC-0216 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Conduct fraud risk assessment for combined entity | Internal Audit | Day 1 | High |  | Finance Leadership |  | Yes
FRC-0217 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Review segregation of duties in combined finance organization | Internal Audit | Day 60-120 | High |  | HR, Finance
FRC-0218 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Integrate acquired entity into SOX testing program | Internal Audit | Day 60-120 | High
FRC-0219 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Establish unified control monitoring and remediation process | Internal Audit | Day 60-120 | Medium
FRC-0220 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Assess purchase accounting controls and journal entry review | Internal Audit | Day 1 | High |  | Consolidation |  | Yes
FRC-0221 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Review access controls for combined financial systems | Internal Audit | Day 60-120 | High |  | IT
FRC-0222 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Develop combined entity internal audit plan | Internal Audit | Year 1-2 | Medium
FRC-0223 | Finance & Accounting | Income Tax | Organization and Governance | Determine combined James Hardie Tax department structure and accountability requirements for Day One | Income Tax | Day 1
FRC-0224 | Finance & Accounting | Income Tax | Organization and Governance | Train staff on Day One Tax processes, as needed | Income Tax | Day 1
FRC-0225 | Finance & Accounting | Income Tax | Tax Compliance | Identify Enterprise global tax processes and compliance and provision obligations | Income Tax | Day 1
FRC-0226 | Finance & Accounting | Income Tax | Tax Compliance | Understand acquisition impact on local tax compliance obligations in each key/material tax jurisdiction | Income Tax | Day 1
FRC-0227 | Finance & Accounting | Income Tax | Tax Compliance | Complete required tax filings | Income Tax | Day 1
FRC-0228 | Finance & Accounting | Income Tax | Tax Compliance | Update global compliance calendars for new reporting requirements | Income Tax | Day 1
FRC-0229 | Finance & Accounting | Income Tax | Tax Compliance | Ensure tax payments can be made globally | Income Tax | Day 1
FRC-0230 | Finance & Accounting | Income Tax | Tax Compliance | Determine Enterprise tax accounting methods and requirements to align to James Hardie accounting methods (i.e. deferred taxes) | Income Tax | Day 1
FRC-0231 | Finance & Accounting | Income Tax | Tax Compliance | Obtain tax depreciation information/schedules for all required assets as of transaction close | Income Tax | Day 1
FRC-0232 | Finance & Accounting | Income Tax | Tax Compliance | Obtain and file Enterprise historical tax filing and audit data to James Hardie (electronic and paper) | Income Tax | Day 1
FRC-0233 | Finance & Accounting | Income Tax | Tax Compliance | Assess Enterprise tax systems and determine integration plan | Income Tax | Day 1
FRC-0234 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Develop transfer pricing documentation for new intercompany flows | Income Tax | Day 1 | High |  | Treasury |  | Yes
FRC-0235 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Analyze tax attribute carryforwards (NOLs, credits) for acquired entity | Income Tax | Day 1 | High |  |  |  | Yes
FRC-0236 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Assess Section 382/383 limitations on acquired tax attributes | Income Tax | Day 1 | High |  | Legal |  | Yes
FRC-0237 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Review VAT/GST registration changes required post-transaction | Income Tax | Day 1 | High |  | Legal |  | Yes
FRC-0238 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Assess indirect tax implications of legal entity restructuring | Income Tax | Day 1 | High |  | Legal, Treasury |  | Yes
FRC-0239 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Update sales and use tax nexus analysis for combined entity | Income Tax | Day 60-120 | Medium |  | Operational Accounting
FRC-0240 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Integrate indirect tax compliance into combined close process | Income Tax | Day 60-120 | Medium |  | Consolidation
FRC-0241 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Align customs and import/export duty processes | Income Tax | Day 60-120 | Medium |  | Operations
FRC-0242 | Operations | Facilities & Indirect Sourcing | Facilities | Complete diligence on existing Real Estate organization | Facilities & Indirect Sourcing | Day 1
FRC-0243 | Operations | Facilities & Indirect Sourcing | Facilities | Design Day One and interim state organization structure | Facilities & Indirect Sourcing | Day 1
FRC-0244 | Operations | Facilities & Indirect Sourcing | Facilities | Estimate synergies related to Day One and interim organization structure | Facilities & Indirect Sourcing | Day 1
FRC-0245 | Operations | Facilities & Indirect Sourcing | Facilities | Inventory and map total real estate holdings | Facilities & Indirect Sourcing | Day 1
FRC-0246 | Operations | Facilities & Indirect Sourcing | Facilities | Collaborate with org design team to understand facility requirements | Facilities & Indirect Sourcing | Day 1
FRC-0247 | Operations | Facilities & Indirect Sourcing | Facilities | Complete review of corporate locations for optimization planning | Facilities & Indirect Sourcing | Day 1
FRC-0248 | Operations | Facilities & Indirect Sourcing | Facilities | Review leases on properties that may be exited post-transaction close to determine if early termination provision exists | Facilities & Indirect Sourcing | Day 1
FRC-0249 | Operations | Facilities & Indirect Sourcing | Facilities | Determine landlords requiring notification or consent letters prior to transaction close | Facilities & Indirect Sourcing | Day 1
FRC-0250 | Operations | Facilities & Indirect Sourcing | Facilities | Notifications and consent letters for required landlords sent out and consent letters received | Facilities & Indirect Sourcing | Day 1
FRC-0251 | Operations | Facilities & Indirect Sourcing | Facilities | Determine go-forward future data management tool for Real Estate of combined company | Facilities & Indirect Sourcing | Day 1
FRC-0252 | Operations | Facilities & Indirect Sourcing | Facilities | Assume lease ownership for sites that are leased by Xella and are being transferred to James Hardie | Facilities & Indirect Sourcing | Day 1
FRC-0253 | Operations | Facilities & Indirect Sourcing | Facilities | Ensure flawless transition and harmonization of facilities management and maintenance | Facilities & Indirect Sourcing | Day 1
FRC-0254 | Operations | Facilities & Indirect Sourcing | Facilities | Ensure appropriate security access changes are reflected in facilities | Facilities & Indirect Sourcing | Day 1
FRC-0255 | Operations | Facilities & Indirect Sourcing | Facilities | Complete migration to single / optimal Real Estate data management tool | Facilities & Indirect Sourcing | Day 60-120
FRC-0256 | Operations | Facilities & Indirect Sourcing | Facilities | Alignment / harmonization of core Real Estate policies, processes & procedures | Facilities & Indirect Sourcing | Day 60-120
FRC-0257 | Operations | Facilities & Indirect Sourcing | Facilities | Implement new combined organization structure | Facilities & Indirect Sourcing | Day 60-120
FRC-0258 | Operations | Facilities & Indirect Sourcing | Facilities | Negotiate lease terminations, concessions and other agreements with landlords to support the real estate consolidation process | Facilities & Indirect Sourcing | Day 60-120
FRC-0259 | Operations | Facilities & Indirect Sourcing | Facilities | Complete survey of properties to determine sign ordinance and approval requirements for new signage | Facilities & Indirect Sourcing | Day 60-120
FRC-0260 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Review and rationalize current indirect spend | Facilities & Indirect Sourcing | Day 1
FRC-0261 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Complete review / diligence on current vendor sourcing and outsourcing contracts | Facilities & Indirect Sourcing | Day 1
FRC-0262 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Revised synergy & one-time cost estimates based on diligence findings | Facilities & Indirect Sourcing | Day 1
FRC-0263 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Review existing vendors for capabilities, quality, and compliance with corporate standards | Facilities & Indirect Sourcing | Day 1
FRC-0264 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Create and implement a supplier vendor certification process | Facilities & Indirect Sourcing | Day 1
FRC-0265 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Achieve optimal vendor sourcing for combined company | Facilities & Indirect Sourcing | Day 1
FRC-0266 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Assess current state metrics and reporting process | Facilities & Indirect Sourcing | Day 1
FRC-0267 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Develop and implement new metrics and reporting capabilities | Facilities & Indirect Sourcing | Day 60-120
FRC-0268 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Complete Day One staffing requirements for combined Treasury | Treasury / Risk Management | Day 1
FRC-0269 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Determine Gaps in Treasury's polices and procedures | Treasury / Risk Management | Day 1
FRC-0270 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Establish combined Treasury policies and controls | Treasury / Risk Management | Day 1
FRC-0271 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Train Enterprise staff on Day One Treasury processes, as needed | Treasury / Risk Management | Day 1
FRC-0272 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Develop a detailed cash flow forecast for pre-acquisition and year one activities |  | Day 1
FRC-0273 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Identify Enterprise and Xella outstanding intercompany loans and settlement plan | Treasury / Risk Management | Day 1
FRC-0274 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Determine interim working capital needs for combined James Hardie | Treasury / Risk Management | Day 1
FRC-0275 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Assess global liquidity needs | Treasury / Risk Management | Day 1
FRC-0276 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Based upon cash flow and inter-company payments determine the optimal interest rat SWAP structure. | Treasury / Risk Management | Day 1
FRC-0277 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Determine requirements for debt instruments (covenants, interest rate swaps) and associated procedures | Treasury / Risk Management | Day 1
FRC-0278 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Identify and evaluate Enterprise procedures for letters of credit execution and monitoring, as needed | Treasury / Risk Management | Day 1
FRC-0279 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Inventory Enterprise banking partners, accounts, and bank contacts | Treasury / Risk Management | Day 1
FRC-0280 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Document the Enterprise / James Hardie combines bank structure | Treasury / Risk Management | Day 1
FRC-0281 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine officers authorized to sign bank mandates | Treasury / Risk Management | Day 1
FRC-0282 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine associates authorized to process electronic payment and sign checks | Treasury / Risk Management | Day 1
FRC-0283 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Review the account analysis statements to determine what bank services are utilized. | Treasury / Risk Management | Day 1
FRC-0284 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine recent cash balances for all banks | Treasury / Risk Management | Day 1
FRC-0285 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Open new bank accounts to support new tax structure and replace existing bank accounts | Treasury / Risk Management | Day 1
FRC-0286 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Provide process change communication to banks providing services on Day One | Treasury / Risk Management | Day 1
FRC-0287 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | After new boards are established, prepare bank resolutions authorized Enterprise / James Hardie officers | Treasury / Risk Management | Day 1
FRC-0288 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Update all bank mandates to authorize new bank officers. | Treasury / Risk Management | Day 60-120
FRC-0289 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Determine if Enterprise issues Corporate credit cards / p-cards to employees. | Treasury / Risk Management | Day 1
FRC-0290 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company. | Treasury / Risk Management | Day 1
FRC-0291 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Review the process to interface credit card with ERP and other systems | Treasury / Risk Management | Day 1
FRC-0292 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Sign a new contract with the credit card company (incumbent or new) | Treasury / Risk Management | Day 1
FRC-0293 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Determine if Enterprise accepts credit card payments from customers | Treasury / Risk Management | Day 1
FRC-0294 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company. | Treasury / Risk Management | Day 1
FRC-0295 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Review the process to interface credit card with ERP and other systems | Treasury / Risk Management | Day 1
FRC-0296 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Sign a new contract with the credit card company (incumbent or new) | Treasury / Risk Management | Day 1
FRC-0297 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Identify and assume control of Enterprise cash globally | Treasury / Risk Management | Day 1
FRC-0298 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine combined James Hardie global cash forecasting and reporting processes | Treasury / Risk Management | Day 1
FRC-0299 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine daily cash concentration and positioning processes for combined James Hardie | Treasury / Risk Management | Day 1
FRC-0300 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Identify all Enterprise ACH debit / credit arrangements (tax, vendor payments) | Treasury / Risk Management | Day 1
FRC-0301 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine procedures and controls for executing electronic fund transfers (EFTs) | Treasury / Risk Management | Day 1
FRC-0302 | Finance & Accounting | Treasury & Risk Mgmt | Foreign Exchange | Determine the non-functional currency balance sheet and cash flow hedge exposures. | Treasury / Risk Management | Day 1
FRC-0303 | Finance & Accounting | Treasury & Risk Mgmt | Determine how the new intercompany structure will impact foreign exchange exposures. | Determine the best way to hedge the combined foreign exchange exposures | Treasury / Risk Management | Day 1
FRC-0304 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Review and evaluate Enterprise exposures insured, limits and deductibles. | Treasury / Risk Management | Day 1
FRC-0305 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Obtain a list of current and former legal entities that need to be insured. If not in the United States, please identify the country incorporated. | Treasury / Risk Management | Day 1
FRC-0306 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Five year history of all open and closed insurance claims. If claims are open, please provide a status update. | Treasury / Risk Management | Day 1
FRC-0307 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Property - list of all locations detailing the address and values by locations (building value, inventory, contents, BI, CBI, and extra expense). | Treasury / Risk Management | Day 1
FRC-0308 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | COPE information for all locations with values in excess of $1M | Treasury / Risk Management | Day 1
FRC-0309 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Property engineering, carrier inspection, and boiler/machinery inspection reports. | Treasury / Risk Management | Day 1
FRC-0310 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Description of interdependencies between locations. | Treasury / Risk Management | Day 1
FRC-0311 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of out-sourced manufacturing relationships including description, related sales/purchase volumes, and process criticality. | Treasury / Risk Management | Day 1
FRC-0312 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of certificates of insurance. | Treasury / Risk Management | Day 1
FRC-0313 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Projected international payroll and employee headcount by country. | Treasury / Risk Management | Day 1
FRC-0314 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Foreign sales to the US, sales from the US to other countries, and sales from international locations to other countries. | Treasury / Risk Management | Day 1
FRC-0315 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of import/export dollar values by product, geography, and type of vessel used to ship product | Treasury / Risk Management | Day 1
FRC-0316 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | Information regarding new associates that will be granted equity options in the first quarter | Treasury / Risk Management | Day 1
FRC-0317 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | Copy of all stock option agreements - PSA/U, RSA/U, SSR… | Treasury / Risk Management | Day 1
FRC-0318 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | List of all employees receiving options, type of option being granted, and number of options / shares | Treasury / Risk Management | Day 1
FRC-0319 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Assess working capital requirements for combined entity | Treasury / Risk Management | Day 1 | High |  | FP&A |  | Yes
FRC-0320 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Analyze cash flow and debt obligations to optimize liquidity | Treasury / Risk Management | Day 1 | High |  | FP&A |  | Yes
FRC-0321 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Monitor covenant compliance for combined debt structure | Treasury / Risk Management | Day 1 | High |  | Legal, FP&A |  | Yes
FRC-0322 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Develop 13-week cash flow forecast for combined entity | Treasury / Risk Management | Day 1 | High |  | FP&A |  | Yes
FRC-0323 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Refinance or restructure acquired company debt as needed | Treasury / Risk Management | Day 1 | High |  | Legal |  | Yes
FRC-0324 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Notify lenders and rating agencies of transaction close | Treasury / Risk Management | Day 1 | High |  | Investor Relations |  | Yes
FRC-0325 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Update capital structure analysis for combined entity | Treasury / Risk Management | Day 60-120 | Medium |  | FP&A
FRC-0326 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Optimize intercompany funding structure for tax efficiency | Treasury / Risk Management | Day 60-120 | Medium |  | Tax
FRC-0327 | Finance & Accounting | FP&A | Organization and Governance | Determine combined James Hardie FP&A department structure and accountability requirements for Day One | FP&A | Day 1
FRC-0328 | Finance & Accounting | FP&A | Organization and Governance | Train FP&A staff on Day One FP&A processes; provide communications on process changes as needed | FP&A | Day 1
FRC-0329 | Finance & Accounting | FP&A | Strategic Planning | Assess Fermacell strategic plan | FP&A | Day 1
FRC-0330 | Finance & Accounting | FP&A | Strategic Planning | Complete strategic planning session in June; includes combined James Hardie considerations | FP&A | Day 1
FRC-0331 | Finance & Accounting | FP&A | Budgeting and Planning | Understand Fermacell budgeting and forecasting processes | FP&A | Day 1
FRC-0332 | Finance & Accounting | FP&A | Budgeting and Planning | Develop combined FP&A Day One budgeting and forecasting processes; determine manual reporting requirements, as needed | FP&A | Day 1
FRC-0333 | Finance & Accounting | FP&A | Budgeting and Planning | Develop and obtain approval on combined James Hardie Day One forecast for interim/transition period | FP&A | Day 1
FRC-0334 | Finance & Accounting | FP&A | Budgeting and Planning | Develop integrated budget process and establish calendar for annual process given transaction close date; calendar to be provided prior to close | FP&A | Day 1
FRC-0335 | Finance & Accounting | FP&A | Budgeting and Planning | Identify combined FP&A budgeting and forecasting roles and responsibilities; communicate accordingly | FP&A | Day 1
FRC-0336 | Finance & Accounting | FP&A | Management Reporting | Identify Fermacell current Management Reporting package; determine all must-have reports | FP&A | Day 1
FRC-0337 | Finance & Accounting | FP&A | Management Reporting | Rationalize James Hardie and Fermacell reports | FP&A | Day 1
FRC-0338 | Finance & Accounting | FP&A | Management Reporting | Determine Combined James Hardie reporting requirements for Day One (reports, format, frequency, distribution); includes 'Flash' reporting process for P&L and Cash | FP&A | Day 1
FRC-0339 | Finance & Accounting | FP&A | Management Reporting | Develop interim reporting calendar and plan for day 90 reporting requirements | FP&A | Day 1
FRC-0340 | Finance & Accounting | FP&A | Management Reporting | Completed combined James Hardie revenue planning kick-off in Oct ‘14 to launch annual process | FP&A | Day 1
FRC-0341 | Finance & Accounting | FP&A | Management Reporting | Compare and align management reporting data definitions (e.g. GL accounts and financial line items) | FP&A | Day 1
FRC-0342 | Finance & Accounting | FP&A | Management Reporting | Communicate combined reporting requirements and processes to stakeholders | FP&A | Day 1
FRC-0343 | Finance & Accounting | FP&A | Management Reporting | Understand Day One reporting requirements for debt financing | FP&A | Day 1
FRC-0344 | Finance & Accounting | FP&A | Performance Management Framework | Identify and review Fermacell current performance indicators/frameworks | FP&A | Day 1
FRC-0345 | Finance & Accounting | FP&A | Performance Management Framework | Agree on Day One KPIs for internal reporting purposes with key stakeholders | FP&A | Day 1
FRC-0346 | Finance & Accounting | FP&A | Systems and Data | Create dimension in Hyperion to store baseline data | FP&A | Day 1
FRC-0347 | Finance & Accounting | FP&A | Systems and Data | Assess Fermacell FP&A systems (e.g., Oracle) and determine level of entanglement with Xella systems | FP&A | Day 1
FRC-0348 | Finance & Accounting | FP&A | Systems and Data | Assess potential risks / disruption to business due to changes to performance management systems | FP&A | Day 1
FRC-0349 | Finance & Accounting | FP&A | Systems and Data | Determine Fermacell migration plan and data | FP&A | Day 1
FRC-0350 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Define financial integration success metrics | FP&A | Day 1 | High |  | PMO |  | Yes
FRC-0351 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Establish baseline measurements for operational efficiency KPIs | FP&A | Day 1 | High |  | Operations |  | Yes
FRC-0352 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Create integration dashboard for executive reporting | FP&A | Day 60-120 | High |  | PMO
FRC-0353 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Track customer satisfaction and retention through integration | FP&A | Day 60-120 | Medium |  | Sales
FRC-0354 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Monitor employee engagement metrics during transition | FP&A | Day 60-120 | Medium |  | HR
FRC-0355 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Identify key finance talent for retention | FP&A | Day 1 | High |  | HR |  | Yes
FRC-0356 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Develop finance organization structure for combined entity | FP&A | Day 1 | High |  | HR |  | Yes
FRC-0357 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Plan retention bonuses for critical finance personnel | FP&A | Day 1 | High |  | HR, Compensation |  | Yes
FRC-0358 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Develop cross-training plan for combined finance team | FP&A | Day 60-120 | Medium |  | HR
FRC-0359 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Implement unified FP&A tools and reporting standards | FP&A | Year 1-2 | Medium |  | IT
FRC-0360 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Conduct interviews with finance workstream leads to understand current finance processes | Baselining | Day 1
FRC-0361 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Identify Finance integration value capture targets | Baselining | Day 1
FRC-0362 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Develop detailed qualitative/quantitative business cases for Finance value capture initiatives | Baselining | Day 1
FRC-0363 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Review value capture initiatives with finance workstream leads | Baselining | Day 1
FRC-0364 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Develop a final validated list of value capture initiatives for the finance function | Baselining | Day 1
FRC-0365 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Review business cases and validate value capture targets with workstream leads | Baselining | Day 1
FRC-0366 | Integration Management | Baselining | Planning for Value Capture | Develop detailed workplans for execution of each approved value driver initiative | Baselining | Day 1
FRC-0367 | Integration Management | Baselining | Planning for Value Capture | Define metrics to track progress towards reaching value capture targets | Baselining | Day 1
FRC-0368 | Integration Management | Baselining | Planning for Value Capture | Develop mechanism to report on value capture activities | Baselining | Day 1
FRC-0369 | Integration Management | Baselining | Planning for Value Capture | Develop high level milestone plan showing value capture targets at various points along the integration timeline | Baselining | Day 1
FRC-0370 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Develop consolidated list of value capture initiatives identified by individual functions | Baselining | Day 1
FRC-0371 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Consolidate business cases developed by individual functions into master | Baselining | Day 1
FRC-0372 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Validate business cases for completeness and validate any assumptions made | Baselining | Day 1
FRC-0373 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Develop a consolidated value capture model across all functions | Baselining | Day 1
FRC-0374 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Validate consolidated value capture targets with cost synergies identified in deal model | Baselining | Day 1
FRC-0375 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Conduct cybersecurity risk assessment of target's IT infrastructure | Cybersecurity | Day 1 | High | Not started | IT |  | Yes
FRC-0376 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Inventory all IT systems, applications, and data repositories | Cybersecurity | Day 1 | High | Not started | IT |  | Yes
FRC-0377 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Review target's data breach history and incident response procedures | Cybersecurity | Day 1 | High | Not started | Legal, IT |  | Yes
FRC-0378 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Assess network security controls and vulnerability management practices | Cybersecurity | Day 1 | High | Not started | IT |  | Yes
FRC-0379 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Review third-party vendor cybersecurity practices and contracts | Cybersecurity | Day 1 | High | Not started | Procurement, Legal |  | Yes
FRC-0380 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Identify cyber insurance coverage and gaps | Cybersecurity | Day 1 | High | Not started | Treasury, Legal |  | Yes
FRC-0381 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Develop IT system integration security plan | Cybersecurity | Day 1 | High | Not started | IT |  | Yes
FRC-0382 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Inventory personal data collected by target (customers, employees, vendors) | Data Privacy | Day 1 | High | Not started | Legal, HR |  | Yes
FRC-0383 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Assess compliance with GDPR, CCPA, and other applicable privacy laws | Data Privacy | Day 1 | High | Not started | Legal |  | Yes
FRC-0384 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Review data processing agreements with third parties | Data Privacy | Day 1 | Medium | Not started | Legal, Procurement
FRC-0385 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Identify cross-border data transfer mechanisms and requirements | Data Privacy | Day 1 | High | Not started | Legal, IT |  | Yes
FRC-0386 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Review privacy policies and customer consent mechanisms | Data Privacy | Day 1 | Medium | Not started | Legal, Marketing
FRC-0387 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Assess data retention policies and practices | Data Privacy | Day 1 | Medium | Not started | Legal, IT
FRC-0388 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Inventory AI tools and automation systems used by target | AI Governance | Day 1 | Medium | Not started | IT, Operations
FRC-0389 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Assess AI-related risks (privacy, IP, bias, employment) | AI Governance | Day 1 | Medium | Not started | Legal, HR
FRC-0390 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Review AI vendor contracts and data usage terms | AI Governance | Day 1 | Medium | Not started | Legal, Procurement
FRC-0391 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Establish combined company data privacy policies | Cybersecurity | Day 60-120 | High | Not started | Legal, HR
FRC-0392 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Complete penetration testing of integrated systems | Cybersecurity | Day 60-120 | High | Not started | IT
FRC-0393 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Implement unified identity and access management (IAM) | Cybersecurity | Day 60-120 | High | Not started | IT, HR
FRC-0394 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Train employees on combined cybersecurity protocols | Cybersecurity | Day 60-120 | High | Not started | HR, IT
FRC-0395 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Migrate to unified security monitoring and incident response | Cybersecurity | Day 60-120 | High | Not started | IT
FRC-0396 | IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | Update cyber insurance coverage for combined entity | Cybersecurity | Day 60-120 | Medium | Not started | Treasury, Legal
FRC-0397 | IT | Cybersecurity & Data Privacy | Long-term Security Integration | Consolidate security tools and platforms | Cybersecurity | Year 1-2 | Medium | Not started | IT
FRC-0398 | IT | Cybersecurity & Data Privacy | Long-term Security Integration | Implement unified data governance framework | Data Privacy | Year 1-2 | Medium | Not started | Legal, IT
FRC-0399 | IT | Cybersecurity & Data Privacy | Long-term Security Integration | Establish ongoing security audit and compliance program | Cybersecurity | Year 1-2 | Medium | Not started | Internal Audit, IT
FRC-0400 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Conduct ESG due diligence on target company | ESG | Day 1 | High | Not started | Legal, Operations |  | Yes
FRC-0401 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Identify material ESG risks and liabilities (environmental, social, governance) | ESG | Day 1 | High | Not started | Legal, Operations |  | Yes
FRC-0402 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Review environmental permits, compliance history, and remediation obligations | ESG | Day 1 | High | Not started | Legal, Facilities |  | Yes
FRC-0403 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Assess target's carbon footprint and emissions data | ESG | Day 1 | Medium | Not started | Operations
FRC-0404 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Review labor practices, health & safety records, and supply chain standards | ESG | Day 1 | High | Not started | HR, Operations |  | Yes
FRC-0405 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Identify applicable ESG reporting requirements (EU CSRD, SEC Climate, TCFD) | ESG | Day 1 | High | Not started | Legal, Finance |  | Yes
FRC-0406 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Assess combined company's ESG disclosure obligations | ESG | Day 1 | High | Not started | Legal, Investor Relations |  | Yes
FRC-0407 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Review target's existing ESG reports and ratings | ESG | Day 1 | Medium | Not started | Investor Relations
FRC-0408 | Legal / Compliance | ESG & Sustainability | Data Collection & Reporting Integration | Inventory ESG data collection systems and processes at target | ESG | Day 60-120 | Medium | Not started | IT, Operations
FRC-0409 | Legal / Compliance | ESG & Sustainability | Data Collection & Reporting Integration | Develop combined ESG data collection framework | ESG | Day 60-120 | High | Not started | Finance, Operations
FRC-0410 | Legal / Compliance | ESG & Sustainability | Data Collection & Reporting Integration | Establish baseline ESG metrics for combined entity | ESG | Day 60-120 | High | Not started | Finance, Operations
FRC-0411 | Legal / Compliance | ESG & Sustainability | Data Collection & Reporting Integration | Integrate ESG reporting into financial close process | ESG | Day 60-120 | Medium | Not started | Consolidation
FRC-0412 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Develop combined company ESG strategy and targets | ESG | Year 1-2 | High | Not started | Strategy, Operations
FRC-0413 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Align sustainability policies and practices across combined entity | ESG | Year 1-2 | Medium | Not started | Operations, HR
FRC-0414 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Implement unified ESG reporting platform | ESG | Year 1-2 | Medium | Not started | IT, Finance
FRC-0415 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Establish ESG governance structure for combined company | ESG | Year 1-2 | High | Not started | Legal, Board
FRC-0416 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Communicate ESG commitments to stakeholders (investors, customers, employees) | ESG | Year 1-2 | Medium | Not started | Investor Relations, Comms
FRC-0417 | Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | Obtain third-party ESG assurance/verification | ESG | Year 1-2 | Medium | Not started | External Audit
FRC-0418 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Develop comprehensive integration budget by workstream | Integration Budget | Day 1 | High | Not started | All Workstreams |  | Yes
FRC-0419 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Identify one-time integration costs vs. ongoing run-rate costs | Integration Budget | Day 1 | High | Not started | FP&A |  | Yes
FRC-0420 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Establish integration cost tracking and reporting cadence | Integration Budget | Day 1 | High | Not started | FP&A, PMO |  | Yes
FRC-0421 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Define cost approval thresholds and governance process | Integration Budget | Day 1 | High | Not started | Finance Leadership |  | Yes
FRC-0422 | Integration Management | Integration Budget & Tracking | Stranded Costs Management | Identify potential stranded costs from TSA exits | Stranded Costs | Day 1 | High | Not started | TSA, FP&A | Yes | Yes
FRC-0423 | Integration Management | Integration Budget & Tracking | Stranded Costs Management | Develop stranded cost mitigation plan | Stranded Costs | Day 1 | High | Not started | All Functions |  | Yes
FRC-0424 | Integration Management | Integration Budget & Tracking | Stranded Costs Management | Track stranded cost run-off timeline | Stranded Costs | Day 60-120 | Medium | Not started | FP&A
FRC-0425 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Develop synergy tracking model aligned with deal model assumptions | Synergy Tracking | Day 1 | High | Not started | FP&A, Corp Dev |  | Yes
FRC-0426 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Define synergy categories (cost, revenue, capital) | Synergy Tracking | Day 1 | High | Not started | FP&A |  | Yes
FRC-0427 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Establish synergy measurement methodology and baseline | Synergy Tracking | Day 1 | High | Not started | FP&A |  | Yes
FRC-0428 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Create synergy tracking dashboard for leadership reporting | Synergy Tracking | Day 60-120 | High | Not started | FP&A
FRC-0429 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Implement monthly synergy realization reporting | Synergy Tracking | Day 60-120 | High | Not started | FP&A
FRC-0430 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Reconcile synergy actuals to deal model projections | Synergy Tracking | Day 60-120 | High | Not started | FP&A, Corp Dev
FRC-0431 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Define integration success metrics and KPIs | KPIs | Day 1 | High | Not started | PMO, FP&A |  | Yes
FRC-0432 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Establish baseline measurements for all KPIs | KPIs | Day 1 | High | Not started | All Workstreams |  | Yes
FRC-0433 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Implement integration scorecard for steering committee | KPIs | Day 60-120 | High | Not started | PMO
FRC-0434 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Track customer satisfaction through integration | KPIs | Day 60-120 | Medium | Not started | Sales, Operations
FRC-0435 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Track employee engagement/retention through integration | KPIs | Day 60-120 | Medium | Not started | HR
FRC-0436 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Develop integration communication plan (internal and external) | Change Mgmt | Day 1 | High | Not started | Comms, HR |  | Yes
FRC-0437 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Establish integration governance structure (PMO, Steering Committee) | Change Mgmt | Day 1 | High | Not started | Executive Leadership |  | Yes
FRC-0438 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Define escalation paths and decision-making protocols | Change Mgmt | Day 1 | High | Not started | PMO |  | Yes
FRC-0439 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Implement regular town halls and integration updates | Change Mgmt | Day 60-120 | Medium | Not started | Comms, HR
FRC-0440 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Develop change management training for managers | Change Mgmt | Day 60-120 | Medium | Not started | HR
FRC-0441 | Integration Management | Integration Budget & Tracking | Post-Integration Review | Conduct integration lessons learned sessions | Post-Integration | Year 1-2 | Medium | Not started | All Workstreams
FRC-0442 | Integration Management | Integration Budget & Tracking | Post-Integration Review | Document integration playbook for future transactions | Post-Integration | Year 1-2 | Medium | Not started | PMO, Corp Dev
FRC-0443 | Integration Management | Integration Budget & Tracking | Post-Integration Review | Final synergy realization assessment vs. deal model | Post-Integration | Year 1-2 | High | Not started | FP&A, Corp Dev

## PRD Taxonomy Map
PRD L1 Domain (FR-4) | Workstream L2 | Section L3 | Item Count | Day 1 Items | Day 60-120 Items | Year 1-2 Items | High Priority | TSA-Related
Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | 9 | 9 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Data Governance (NEW) | 3 | 1 | 2 | 0 | 1 | 0
Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | 17 | 16 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | 3 | 3 | 0 | 0 | 3 | 0
Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | 7 | 7 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | 8 | 7 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | 3 | 3 | 0 | 0 | 3 | 0
Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | 8 | 8 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | 7 | 7 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | 14 | 12 | 2 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Consolidation & Ext. Repo | Training and access | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Budgeting and Planning | 5 | 5 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | 5 | 2 | 3 | 0 | 3 | 0
Finance & Accounting | FP&A | Management Reporting | 8 | 8 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Organization and Governance | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Performance Management Framework | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Strategic Planning | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Systems and Data | 4 | 4 | 0 | 0 | 0 | 0
Finance & Accounting | FP&A | Talent & Organization (NEW) | 5 | 3 | 1 | 1 | 3 | 0
Finance & Accounting | Income Tax | Indirect Tax (NEW) | 5 | 2 | 3 | 0 | 2 | 0
Finance & Accounting | Income Tax | Organization and Governance | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | Income Tax | Tax Compliance | 9 | 9 | 0 | 0 | 0 | 0
Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | 3 | 3 | 0 | 0 | 3 | 0
Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | 9 | 4 | 4 | 1 | 7 | 0
Finance & Accounting | Internal Controls | Internal Audit | 14 | 13 | 0 | 0 | 0 | 2
Finance & Accounting | Operational Accounting | Accounts payable | 4 | 2 | 2 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | 4 | 3 | 1 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Accounts receivable - billing | 6 | 6 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | 8 | 8 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Cash management | 5 | 5 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Contracts | 2 | 2 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Fixed assets | 6 | 6 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | General Ledger - close the books | 10 | 7 | 3 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Intercompany elimination | 7 | 7 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Inventory | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Payroll | 8 | 6 | 1 | 1 | 0 | 0
Finance & Accounting | Operational Accounting | Projects and Initiatives | 5 | 5 | 0 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Revenue recognition policies | 9 | 8 | 1 | 0 | 0 | 0
Finance & Accounting | Operational Accounting | Wire and electronic transfers | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | 10 | 9 | 1 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Cash Management | 5 | 5 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | 4 | 4 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | 4 | 2 | 2 | 0 | 2 | 0
Finance & Accounting | Treasury & Risk Mgmt | Determine how the new intercompany structure will impact foreign exchange exposures. | 1 | 1 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | 3 | 3 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | 7 | 7 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Foreign Exchange | 1 | 1 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Insurance | 12 | 12 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | 4 | 4 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | 4 | 4 | 0 | 0 | 0 | 0
Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | 4 | 4 | 0 | 0 | 4 | 0
IT | Cybersecurity & Data Privacy | AI & Automation Governance | 3 | 3 | 0 | 0 | 0 | 0
IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | 7 | 7 | 0 | 0 | 7 | 0
IT | Cybersecurity & Data Privacy | Data Privacy Compliance | 6 | 6 | 0 | 0 | 3 | 0
IT | Cybersecurity & Data Privacy | Integration & Post-Close Security | 6 | 0 | 6 | 0 | 5 | 0
IT | Cybersecurity & Data Privacy | Long-term Security Integration | 3 | 0 | 0 | 3 | 0 | 0
Integration Management | Baselining | Identification of Finance Value Capture Opportunities | 6 | 6 | 0 | 0 | 0 | 0
Integration Management | Baselining | Planning for Value Capture | 4 | 4 | 0 | 0 | 0 | 0
Integration Management | Baselining | Validation of value capture initiatives for other functions | 5 | 5 | 0 | 0 | 0 | 0
Integration Management | Integration Budget & Tracking | Communication & Change Management | 5 | 3 | 2 | 0 | 3 | 0
Integration Management | Integration Budget & Tracking | Integration Budget Planning | 4 | 4 | 0 | 0 | 4 | 0
Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | 5 | 2 | 3 | 0 | 3 | 0
Integration Management | Integration Budget & Tracking | Post-Integration Review | 3 | 0 | 0 | 3 | 1 | 0
Integration Management | Integration Budget & Tracking | Stranded Costs Management | 3 | 2 | 1 | 0 | 2 | 1
Integration Management | Integration Budget & Tracking | Synergy Tracking | 6 | 3 | 3 | 0 | 6 | 0
Legal / Compliance | ESG & Sustainability | Data Collection & Reporting Integration | 4 | 0 | 4 | 0 | 2 | 0
Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | 5 | 5 | 0 | 0 | 4 | 0
Legal / Compliance | ESG & Sustainability | Regulatory Compliance | 3 | 3 | 0 | 0 | 2 | 0
Legal / Compliance | ESG & Sustainability | Strategy & Long-term Integration | 6 | 0 | 0 | 6 | 2 | 0
Operations | Facilities & Indirect Sourcing | Facilities | 18 | 13 | 5 | 0 | 0 | 0
Operations | Facilities & Indirect Sourcing | Indirect Sourcing | 8 | 7 | 1 | 0 | 0 | 0
TSA / Deal Structure | TSA | Assessment of Service needs | 9 | 9 | 0 | 0 | 0 | 9
TSA / Deal Structure | TSA | Governance and Invoicing Process | 5 | 5 | 0 | 0 | 0 | 5
TSA / Deal Structure | TSA | Schedule of TSA services | 8 | 8 | 0 | 0 | 0 | 8
TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | 7 | 2 | 3 | 2 | 3 | 7

## Phase Timeline View
Workstream | Day 1 | Day 30 | Day 60-120 | Year 1-2 | Total
Baselining | 15 | 0 | 0 | 0 | 15
Consolidation & Ext. Repo | 84 | 0 | 4 | 0 | 88
Cybersecurity & Data Privacy | 16 | 0 | 6 | 3 | 25
ESG & Sustainability | 8 | 0 | 4 | 6 | 18
FP&A | 28 | 0 | 4 | 1 | 33
Facilities & Indirect Sourcing | 20 | 0 | 6 | 0 | 26
Income Tax | 16 | 0 | 3 | 0 | 19
Integration Budget & Tracking | 14 | 0 | 9 | 3 | 26
Internal Controls | 17 | 1 | 4 | 1 | 23
Operational Accounting | 71 | 0 | 8 | 1 | 80
TSA | 24 | 0 | 3 | 2 | 29
Treasury & Risk Mgmt | 56 | 0 | 3 | 0 | 59
TOTAL | 369 | 1 | 54 | 17 | 441

## Importance Matrix
Workstream | High | Medium | Low | Unspecified | Total | % High
TSA | 3 | 1 | 0 | 25 | 29 | 10.34%
Consolidation & Ext. Repo | 7 | 2 | 0 | 81 | 90 | 7.778%
Operational Accounting | 0 | 0 | 0 | 80 | 80 | 0%
Internal Controls | 7 | 2 | 0 | 14 | 23 | 30.43%
Income Tax | 5 | 3 | 0 | 11 | 19 | 26.32%
Facilities & Indirect Sourcing | 0 | 0 | 0 | 26 | 26 | 0%
Treasury & Risk Mgmt | 6 | 2 | 0 | 51 | 59 | 10.17%
FP&A | 6 | 4 | 0 | 23 | 33 | 18.18%
Baselining | 0 | 0 | 0 | 15 | 15 | 0%
Cybersecurity & Data Privacy | 15 | 10 | 0 | 0 | 25 | 60%
ESG & Sustainability | 10 | 8 | 0 | 0 | 18 | 55.56%
Integration Budget & Tracking | 19 | 7 | 0 | 0 | 26 | 73.08%
TOTAL | 78 | 39 | 0 | 326 | 443 | 17.61%

## Dependencies
Item_ID | Workstream | Deliverable | Dependencies | Phase | Importance
FRC-0111 | Consolidation & Ext. Repo | Develop pro forma financial model for combined entity | FP&A | Day 1 | High
FRC-0112 | Consolidation & Ext. Repo | Create model of expected revenue synergies and cost savings | FP&A, Corp Dev | Day 1 | High
FRC-0113 | Consolidation & Ext. Repo | Establish data retention protocols for acquired company financial data | IT, Legal | Day 1 | High
FRC-0114 | Consolidation & Ext. Repo | Identify IFRS vs. GAAP accounting differences between entities | Technical Accounting | Day 1 | High
FRC-0115 | Consolidation & Ext. Repo | Develop IFRS/GAAP reconciliation procedures | Technical Accounting | Day 1 | High
FRC-0116 | Consolidation & Ext. Repo | Determine reporting framework for combined entity | Legal, Technical Accounting | Day 1 | High
FRC-0117 | Consolidation & Ext. Repo | Audit acquired company's financial data quality and completeness | IT, Internal Audit | Day 1 | High
FRC-0118 | Consolidation & Ext. Repo | Establish combined company data governance framework | IT, Finance | Day 60-120 | Medium
FRC-0119 | Consolidation & Ext. Repo | Define master data management approach for combined entity | IT | Day 60-120 | Medium
FRC-0375 | Cybersecurity & Data Privacy | Conduct cybersecurity risk assessment of target's IT infrastructure | IT | Day 1 | High
FRC-0376 | Cybersecurity & Data Privacy | Inventory all IT systems, applications, and data repositories | IT | Day 1 | High
FRC-0377 | Cybersecurity & Data Privacy | Review target's data breach history and incident response procedures | Legal, IT | Day 1 | High
FRC-0378 | Cybersecurity & Data Privacy | Assess network security controls and vulnerability management practices | IT | Day 1 | High
FRC-0379 | Cybersecurity & Data Privacy | Review third-party vendor cybersecurity practices and contracts | Procurement, Legal | Day 1 | High
FRC-0380 | Cybersecurity & Data Privacy | Identify cyber insurance coverage and gaps | Treasury, Legal | Day 1 | High
FRC-0381 | Cybersecurity & Data Privacy | Develop IT system integration security plan | IT | Day 1 | High
FRC-0382 | Cybersecurity & Data Privacy | Inventory personal data collected by target (customers, employees, vendors) | Legal, HR | Day 1 | High
FRC-0383 | Cybersecurity & Data Privacy | Assess compliance with GDPR, CCPA, and other applicable privacy laws | Legal | Day 1 | High
FRC-0384 | Cybersecurity & Data Privacy | Review data processing agreements with third parties | Legal, Procurement | Day 1 | Medium
FRC-0385 | Cybersecurity & Data Privacy | Identify cross-border data transfer mechanisms and requirements | Legal, IT | Day 1 | High
FRC-0386 | Cybersecurity & Data Privacy | Review privacy policies and customer consent mechanisms | Legal, Marketing | Day 1 | Medium
FRC-0387 | Cybersecurity & Data Privacy | Assess data retention policies and practices | Legal, IT | Day 1 | Medium
FRC-0388 | Cybersecurity & Data Privacy | Inventory AI tools and automation systems used by target | IT, Operations | Day 1 | Medium
FRC-0389 | Cybersecurity & Data Privacy | Assess AI-related risks (privacy, IP, bias, employment) | Legal, HR | Day 1 | Medium
FRC-0390 | Cybersecurity & Data Privacy | Review AI vendor contracts and data usage terms | Legal, Procurement | Day 1 | Medium
FRC-0391 | Cybersecurity & Data Privacy | Establish combined company data privacy policies | Legal, HR | Day 60-120 | High
FRC-0392 | Cybersecurity & Data Privacy | Complete penetration testing of integrated systems | IT | Day 60-120 | High
FRC-0393 | Cybersecurity & Data Privacy | Implement unified identity and access management (IAM) | IT, HR | Day 60-120 | High
FRC-0394 | Cybersecurity & Data Privacy | Train employees on combined cybersecurity protocols | HR, IT | Day 60-120 | High
FRC-0395 | Cybersecurity & Data Privacy | Migrate to unified security monitoring and incident response | IT | Day 60-120 | High
FRC-0396 | Cybersecurity & Data Privacy | Update cyber insurance coverage for combined entity | Treasury, Legal | Day 60-120 | Medium
FRC-0397 | Cybersecurity & Data Privacy | Consolidate security tools and platforms | IT | Year 1-2 | Medium
FRC-0398 | Cybersecurity & Data Privacy | Implement unified data governance framework | Legal, IT | Year 1-2 | Medium
FRC-0399 | Cybersecurity & Data Privacy | Establish ongoing security audit and compliance program | Internal Audit, IT | Year 1-2 | Medium
FRC-0400 | ESG & Sustainability | Conduct ESG due diligence on target company | Legal, Operations | Day 1 | High
FRC-0401 | ESG & Sustainability | Identify material ESG risks and liabilities (environmental, social, governance) | Legal, Operations | Day 1 | High
FRC-0402 | ESG & Sustainability | Review environmental permits, compliance history, and remediation obligations | Legal, Facilities | Day 1 | High
FRC-0403 | ESG & Sustainability | Assess target's carbon footprint and emissions data | Operations | Day 1 | Medium
FRC-0404 | ESG & Sustainability | Review labor practices, health & safety records, and supply chain standards | HR, Operations | Day 1 | High
FRC-0405 | ESG & Sustainability | Identify applicable ESG reporting requirements (EU CSRD, SEC Climate, TCFD) | Legal, Finance | Day 1 | High
FRC-0406 | ESG & Sustainability | Assess combined company's ESG disclosure obligations | Legal, Investor Relations | Day 1 | High
FRC-0407 | ESG & Sustainability | Review target's existing ESG reports and ratings | Investor Relations | Day 1 | Medium
FRC-0408 | ESG & Sustainability | Inventory ESG data collection systems and processes at target | IT, Operations | Day 60-120 | Medium
FRC-0409 | ESG & Sustainability | Develop combined ESG data collection framework | Finance, Operations | Day 60-120 | High
FRC-0410 | ESG & Sustainability | Establish baseline ESG metrics for combined entity | Finance, Operations | Day 60-120 | High
FRC-0411 | ESG & Sustainability | Integrate ESG reporting into financial close process | Consolidation | Day 60-120 | Medium
FRC-0412 | ESG & Sustainability | Develop combined company ESG strategy and targets | Strategy, Operations | Year 1-2 | High
FRC-0413 | ESG & Sustainability | Align sustainability policies and practices across combined entity | Operations, HR | Year 1-2 | Medium
FRC-0414 | ESG & Sustainability | Implement unified ESG reporting platform | IT, Finance | Year 1-2 | Medium
FRC-0415 | ESG & Sustainability | Establish ESG governance structure for combined company | Legal, Board | Year 1-2 | High
FRC-0416 | ESG & Sustainability | Communicate ESG commitments to stakeholders (investors, customers, employees) | Investor Relations, Comms | Year 1-2 | Medium
FRC-0417 | ESG & Sustainability | Obtain third-party ESG assurance/verification | External Audit | Year 1-2 | Medium
FRC-0350 | FP&A | Define financial integration success metrics | PMO | Day 1 | High
FRC-0351 | FP&A | Establish baseline measurements for operational efficiency KPIs | Operations | Day 1 | High
FRC-0355 | FP&A | Identify key finance talent for retention | HR | Day 1 | High
FRC-0356 | FP&A | Develop finance organization structure for combined entity | HR | Day 1 | High
FRC-0357 | FP&A | Plan retention bonuses for critical finance personnel | HR, Compensation | Day 1 | High
FRC-0352 | FP&A | Create integration dashboard for executive reporting | PMO | Day 60-120 | High
FRC-0353 | FP&A | Track customer satisfaction and retention through integration | Sales | Day 60-120 | Medium
FRC-0354 | FP&A | Monitor employee engagement metrics during transition | HR | Day 60-120 | Medium
FRC-0358 | FP&A | Develop cross-training plan for combined finance team | HR | Day 60-120 | Medium
FRC-0359 | FP&A | Implement unified FP&A tools and reporting standards | IT | Year 1-2 | Medium
FRC-0234 | Income Tax | Develop transfer pricing documentation for new intercompany flows | Treasury | Day 1 | High
FRC-0236 | Income Tax | Assess Section 382/383 limitations on acquired tax attributes | Legal | Day 1 | High
FRC-0237 | Income Tax | Review VAT/GST registration changes required post-transaction | Legal | Day 1 | High
FRC-0238 | Income Tax | Assess indirect tax implications of legal entity restructuring | Legal, Treasury | Day 1 | High
FRC-0239 | Income Tax | Update sales and use tax nexus analysis for combined entity | Operational Accounting | Day 60-120 | Medium
FRC-0240 | Income Tax | Integrate indirect tax compliance into combined close process | Consolidation | Day 60-120 | Medium
FRC-0241 | Income Tax | Align customs and import/export duty processes | Operations | Day 60-120 | Medium
FRC-0418 | Integration Budget & Tracking | Develop comprehensive integration budget by workstream | All Workstreams | Day 1 | High
FRC-0419 | Integration Budget & Tracking | Identify one-time integration costs vs. ongoing run-rate costs | FP&A | Day 1 | High
FRC-0420 | Integration Budget & Tracking | Establish integration cost tracking and reporting cadence | FP&A, PMO | Day 1 | High
FRC-0421 | Integration Budget & Tracking | Define cost approval thresholds and governance process | Finance Leadership | Day 1 | High
FRC-0422 | Integration Budget & Tracking | Identify potential stranded costs from TSA exits | TSA, FP&A | Day 1 | High
FRC-0423 | Integration Budget & Tracking | Develop stranded cost mitigation plan | All Functions | Day 1 | High
FRC-0425 | Integration Budget & Tracking | Develop synergy tracking model aligned with deal model assumptions | FP&A, Corp Dev | Day 1 | High
FRC-0426 | Integration Budget & Tracking | Define synergy categories (cost, revenue, capital) | FP&A | Day 1 | High
FRC-0427 | Integration Budget & Tracking | Establish synergy measurement methodology and baseline | FP&A | Day 1 | High
FRC-0431 | Integration Budget & Tracking | Define integration success metrics and KPIs | PMO, FP&A | Day 1 | High
FRC-0432 | Integration Budget & Tracking | Establish baseline measurements for all KPIs | All Workstreams | Day 1 | High
FRC-0436 | Integration Budget & Tracking | Develop integration communication plan (internal and external) | Comms, HR | Day 1 | High
FRC-0437 | Integration Budget & Tracking | Establish integration governance structure (PMO, Steering Committee) | Executive Leadership | Day 1 | High
FRC-0438 | Integration Budget & Tracking | Define escalation paths and decision-making protocols | PMO | Day 1 | High
FRC-0424 | Integration Budget & Tracking | Track stranded cost run-off timeline | FP&A | Day 60-120 | Medium
FRC-0428 | Integration Budget & Tracking | Create synergy tracking dashboard for leadership reporting | FP&A | Day 60-120 | High
FRC-0429 | Integration Budget & Tracking | Implement monthly synergy realization reporting | FP&A | Day 60-120 | High
FRC-0430 | Integration Budget & Tracking | Reconcile synergy actuals to deal model projections | FP&A, Corp Dev | Day 60-120 | High
FRC-0433 | Integration Budget & Tracking | Implement integration scorecard for steering committee | PMO | Day 60-120 | High
FRC-0434 | Integration Budget & Tracking | Track customer satisfaction through integration | Sales, Operations | Day 60-120 | Medium
FRC-0435 | Integration Budget & Tracking | Track employee engagement/retention through integration | HR | Day 60-120 | Medium
FRC-0439 | Integration Budget & Tracking | Implement regular town halls and integration updates | Comms, HR | Day 60-120 | Medium
FRC-0440 | Integration Budget & Tracking | Develop change management training for managers | HR | Day 60-120 | Medium
FRC-0441 | Integration Budget & Tracking | Conduct integration lessons learned sessions | All Workstreams | Year 1-2 | Medium
FRC-0442 | Integration Budget & Tracking | Document integration playbook for future transactions | PMO, Corp Dev | Year 1-2 | Medium
FRC-0443 | Integration Budget & Tracking | Final synergy realization assessment vs. deal model | FP&A, Corp Dev | Year 1-2 | High
FRC-0214 | Internal Controls | Design controls for new intercompany transactions | Operational Accounting | Day 1 | High
FRC-0215 | Internal Controls | Assess IT General Controls (ITGC) for acquired systems | IT | Day 1 | High
FRC-0216 | Internal Controls | Conduct fraud risk assessment for combined entity | Finance Leadership | Day 1 | High
FRC-0220 | Internal Controls | Assess purchase accounting controls and journal entry review | Consolidation | Day 1 | High
FRC-0217 | Internal Controls | Review segregation of duties in combined finance organization | HR, Finance | Day 60-120 | High
FRC-0221 | Internal Controls | Review access controls for combined financial systems | IT | Day 60-120 | High
FRC-0024 | TSA | Identify stranded costs associated with TSA exits | FP&A | Day 1 | High
FRC-0026 | TSA | Create TSA wind-down communication plan with seller | Legal | Day 60-120
FRC-0027 | TSA | Track TSA cost vs. internal capability build costs | FP&A | Day 60-120 | Medium
FRC-0028 | TSA | Execute TSA termination notices per contractual requirements | Legal | Year 1-2 | High
FRC-0029 | TSA | Complete knowledge transfer from TSA providers | All Functions | Year 1-2 | High
FRC-0319 | Treasury & Risk Mgmt | Assess working capital requirements for combined entity | FP&A | Day 1 | High
FRC-0320 | Treasury & Risk Mgmt | Analyze cash flow and debt obligations to optimize liquidity | FP&A | Day 1 | High
FRC-0321 | Treasury & Risk Mgmt | Monitor covenant compliance for combined debt structure | Legal, FP&A | Day 1 | High
FRC-0322 | Treasury & Risk Mgmt | Develop 13-week cash flow forecast for combined entity | FP&A | Day 1 | High
FRC-0323 | Treasury & Risk Mgmt | Refinance or restructure acquired company debt as needed | Legal | Day 1 | High
FRC-0324 | Treasury & Risk Mgmt | Notify lenders and rating agencies of transaction close | Investor Relations | Day 1 | High
FRC-0325 | Treasury & Risk Mgmt | Update capital structure analysis for combined entity | FP&A | Day 60-120 | Medium
FRC-0326 | Treasury & Risk Mgmt | Optimize intercompany funding structure for tax efficiency | Tax | Day 60-120 | Medium

## Day 1 Critical Path
Item_ID | PRD_L1_Domain | Workstream | Section | Deliverable | Importance | Dependencies
FRC-0033 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Obtain policies and procedures on monthly close and close schedule with cut-offs and timing
FRC-0034 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Establish the NewCo financial close calendar
FRC-0035 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Review functional currencie of all Fermacells entities and address changes, as needed
FRC-0036 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Develop task list for monthly consolidation combined company close
FRC-0037 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Develop contingency plan for potential mid-month close(i.e., stub period) dependent on anti-trust approvals
FRC-0038 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Review task list for monthly / quarterly reporting
FRC-0039 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Document trial balance submission timing to align with Fermacell entities
FRC-0040 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Test upload/input format file
FRC-0041 | Finance & Accounting | Consolidation & Ext. Repo | Consolidation - close the books | Perform trial balances submission in consolidation system
FRC-0117 | Finance & Accounting | Consolidation & Ext. Repo | Data Governance (NEW) | Audit acquired company's financial data quality and completeness | High | IT, Internal Audit
FRC-0042 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand the IT landscape for consolidation and reporting structures by product line and geographical area
FRC-0043 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand James Hardie / Fermacell consolidation procedures (upload, journal entries, etc.)
FRC-0044 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Understand Fermacell account structure (custom dimensions, cost center, etc.)
FRC-0046 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Create org structure/codes in consolidation system based on legal/tax structure
FRC-0047 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Review Fermacell chart of accounts and identifes differences
FRC-0048 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Develop the approach to managing multiple chart of accounts
FRC-0049 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Determine approach for chart of account mapping between Fermacell/James Hardie (Fermacell Oracle to James Hardie Oracle, Fermacell Oracle to James Hardie Hyperion)
FRC-0050 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Map Fermacell chart of accounts to James Hardie chart of accounts
FRC-0051 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Identify new accounts to be created,closed or renamed
FRC-0052 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Identify I/C accounts to assign intercompany partner
FRC-0053 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Map intercompany accounts to intercompany partner
FRC-0054 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Review preliminary mapping with technical accounting and flag accounts requiring attention
FRC-0055 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Communicate with reporting FP&A teams to understand reporting requirements/decisions
FRC-0056 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Consider impact of further system implementation on mapping (e.g. Hyperion redesign)
FRC-0057 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Build of FDM Mapping Tables
FRC-0058 | Finance & Accounting | Consolidation & Ext. Repo | Day 1 consolidation model / chart of account mapping | Test and validate mapping tables
FRC-0114 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Identify IFRS vs. GAAP accounting differences between entities | High | Technical Accounting
FRC-0115 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Develop IFRS/GAAP reconciliation procedures | High | Technical Accounting
FRC-0116 | Finance & Accounting | Consolidation & Ext. Repo | IFRS / GAAP Alignment (if cross-border) | Determine reporting framework for combined entity | High | Legal, Technical Accounting
FRC-0061 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Perform inventory of I/C relationships
FRC-0062 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Assess integration impact on current and expected intercompany transactions
FRC-0063 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.)
FRC-0064 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Understand multi-arrangements transactions and assess materiality, if any
FRC-0065 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Assess current process for capturing intercompany activity and assess applicability to current business requirements
FRC-0066 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell
FRC-0067 | Finance & Accounting | Consolidation & Ext. Repo | Intercompany elimination | Create new intercompany trading partners and accounts
FRC-0030 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Understand current James Hardie and Fermacell org structures including roles and responsibilities
FRC-0031 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Identify key contacts/counterparts across the regions
FRC-0032 | Finance & Accounting | Consolidation & Ext. Repo | Mobilization and data gathering | Gather and share org chart, chart of accounts, entity listing, currencies, etc. between Fermacell and James Hardie
FRC-0071 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Collect and review all policies, standards and procedures
FRC-0072 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Perform policy gap analysis to understand accounting difference between Fermacell and James Hardie
FRC-0073 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Assess materiality of difference in accounting policy
FRC-0074 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Understand new accounting policies required as result of the merger
FRC-0075 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Prioritize accounting policies to be developed requiring Day 1 alignment
FRC-0076 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Develop revised or common policies and procedures
FRC-0077 | Finance & Accounting | Consolidation & Ext. Repo | Policies, procedures, and documentation | Obtain approval from policy steering committee
FRC-0111 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Develop pro forma financial model for combined entity | High | FP&A
FRC-0112 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Create model of expected revenue synergies and cost savings | High | FP&A, Corp Dev
FRC-0113 | Finance & Accounting | Consolidation & Ext. Repo | Pro Forma & Synergy Modeling (NEW) | Establish data retention protocols for acquired company financial data | High | IT, Legal
FRC-0068 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Obtain listing of purchase accounting adjustments based on draft and final valuation reports
FRC-0069 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Determine approach and confirm push-down level of purchase accounting entries (entity, country, regional, corporate)
FRC-0070 | Finance & Accounting | Consolidation & Ext. Repo | Purchase accounting and corporate policies | Confirm feasibility and document push-down approach
FRC-0100 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Obtain both company close packages and identify unique key performance indicators
FRC-0101 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Understand current reporting responsibilities, systems and processes
FRC-0102 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Agree upon the combined company key performance indicators for reporting purposes
FRC-0103 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Validate availability of information within accounting close function
FRC-0104 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Review key performance indicators and management reporting package with investor relations
FRC-0105 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Design the combined company interim close packages
FRC-0106 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Agree upon reporting requirements and key stakeholders (including credit agencies and other reporting needs)
FRC-0107 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - management | Train personnel on financial information available and discussion/narrative requirements
FRC-0093 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Understand current system processes to perform statutory reports
FRC-0094 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Inventory all reporting requirements and status of each
FRC-0095 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Update inventory based upon local legal merger
FRC-0096 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Determine valuation requirements for local tax mergers
FRC-0097 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Engage appraiser, as necessary
FRC-0098 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Structure opening balance sheet accounting based upon local legal merger plan
FRC-0099 | Finance & Accounting | Consolidation & Ext. Repo | Reporting - statutory | Link transaction accounting to local legal merger plan
FRC-0079 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Identify main differences between James Hardie and Fermacell disclosures
FRC-0080 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Identify new accounts to be created to support SEC disclosures/accounts roll forward
FRC-0081 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Prepare historical combined company financial statements and key performance indicators
FRC-0082 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop plan to produce 8-K reporting required Day 4 post-close and identify data requirements
FRC-0083 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop plan to produce Offering Memorandum (OM) post-close and identify data requirements
FRC-0084 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Agree upon NewCo financial statement reporting requirements
FRC-0085 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Determine James Hardie and Fermacell’s Day 1 reporting segments
FRC-0086 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft outline of NewCo interim financial statements for review
FRC-0087 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft purchase accounting footnote
FRC-0088 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Draft pro forma financial statements
FRC-0089 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Develop merger related disclosures (e.g., stock compensation)
FRC-0090 | Finance & Accounting | Consolidation & Ext. Repo | SEC & other regulatory reporting readiness | Submit Offering Memorandum (OM) post- Day 1
FRC-0108 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Review and compare James Hardie and Fermacell cash flow statement models and identify gaps
FRC-0109 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Develop process to produce combined statement of cash flows
FRC-0110 | Finance & Accounting | Consolidation & Ext. Repo | Statement of cash flow | Prepare combined cash flow statement for SEC filing
FRC-0059 | Finance & Accounting | Consolidation & Ext. Repo | Training and access | Provide system access, as necessary
FRC-0060 | Finance & Accounting | Consolidation & Ext. Repo | Training and access | Train identified employees on system applications
FRC-0331 | Finance & Accounting | FP&A | Budgeting and Planning | Understand Fermacell budgeting and forecasting processes
FRC-0332 | Finance & Accounting | FP&A | Budgeting and Planning | Develop combined FP&A Day One budgeting and forecasting processes; determine manual reporting requirements, as needed
FRC-0333 | Finance & Accounting | FP&A | Budgeting and Planning | Develop and obtain approval on combined James Hardie Day One forecast for interim/transition period
FRC-0334 | Finance & Accounting | FP&A | Budgeting and Planning | Develop integrated budget process and establish calendar for annual process given transaction close date; calendar to be provided prior to close
FRC-0335 | Finance & Accounting | FP&A | Budgeting and Planning | Identify combined FP&A budgeting and forecasting roles and responsibilities; communicate accordingly
FRC-0350 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Define financial integration success metrics | High | PMO
FRC-0351 | Finance & Accounting | FP&A | Integration KPIs & Success Metrics (NEW) | Establish baseline measurements for operational efficiency KPIs | High | Operations
FRC-0336 | Finance & Accounting | FP&A | Management Reporting | Identify Fermacell current Management Reporting package; determine all must-have reports
FRC-0337 | Finance & Accounting | FP&A | Management Reporting | Rationalize James Hardie and Fermacell reports
FRC-0338 | Finance & Accounting | FP&A | Management Reporting | Determine Combined James Hardie reporting requirements for Day One (reports, format, frequency, distribution); includes 'Flash' reporting process for P&L and Cash
FRC-0339 | Finance & Accounting | FP&A | Management Reporting | Develop interim reporting calendar and plan for day 90 reporting requirements
FRC-0340 | Finance & Accounting | FP&A | Management Reporting | Completed combined James Hardie revenue planning kick-off in Oct ‘14 to launch annual process
FRC-0341 | Finance & Accounting | FP&A | Management Reporting | Compare and align management reporting data definitions (e.g. GL accounts and financial line items)
FRC-0342 | Finance & Accounting | FP&A | Management Reporting | Communicate combined reporting requirements and processes to stakeholders
FRC-0343 | Finance & Accounting | FP&A | Management Reporting | Understand Day One reporting requirements for debt financing
FRC-0327 | Finance & Accounting | FP&A | Organization and Governance | Determine combined James Hardie FP&A department structure and accountability requirements for Day One
FRC-0328 | Finance & Accounting | FP&A | Organization and Governance | Train FP&A staff on Day One FP&A processes; provide communications on process changes as needed
FRC-0344 | Finance & Accounting | FP&A | Performance Management Framework | Identify and review Fermacell current performance indicators/frameworks
FRC-0345 | Finance & Accounting | FP&A | Performance Management Framework | Agree on Day One KPIs for internal reporting purposes with key stakeholders
FRC-0329 | Finance & Accounting | FP&A | Strategic Planning | Assess Fermacell strategic plan
FRC-0330 | Finance & Accounting | FP&A | Strategic Planning | Complete strategic planning session in June; includes combined James Hardie considerations
FRC-0346 | Finance & Accounting | FP&A | Systems and Data | Create dimension in Hyperion to store baseline data
FRC-0347 | Finance & Accounting | FP&A | Systems and Data | Assess Fermacell FP&A systems (e.g., Oracle) and determine level of entanglement with Xella systems
FRC-0348 | Finance & Accounting | FP&A | Systems and Data | Assess potential risks / disruption to business due to changes to performance management systems
FRC-0349 | Finance & Accounting | FP&A | Systems and Data | Determine Fermacell migration plan and data
FRC-0355 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Identify key finance talent for retention | High | HR
FRC-0356 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Develop finance organization structure for combined entity | High | HR
FRC-0357 | Finance & Accounting | FP&A | Talent & Organization (NEW) | Plan retention bonuses for critical finance personnel | High | HR, Compensation
FRC-0237 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Review VAT/GST registration changes required post-transaction | High | Legal
FRC-0238 | Finance & Accounting | Income Tax | Indirect Tax (NEW) | Assess indirect tax implications of legal entity restructuring | High | Legal, Treasury
FRC-0223 | Finance & Accounting | Income Tax | Organization and Governance | Determine combined James Hardie Tax department structure and accountability requirements for Day One
FRC-0224 | Finance & Accounting | Income Tax | Organization and Governance | Train staff on Day One Tax processes, as needed
FRC-0225 | Finance & Accounting | Income Tax | Tax Compliance | Identify Enterprise global tax processes and compliance and provision obligations
FRC-0226 | Finance & Accounting | Income Tax | Tax Compliance | Understand acquisition impact on local tax compliance obligations in each key/material tax jurisdiction
FRC-0227 | Finance & Accounting | Income Tax | Tax Compliance | Complete required tax filings
FRC-0228 | Finance & Accounting | Income Tax | Tax Compliance | Update global compliance calendars for new reporting requirements
FRC-0229 | Finance & Accounting | Income Tax | Tax Compliance | Ensure tax payments can be made globally
FRC-0230 | Finance & Accounting | Income Tax | Tax Compliance | Determine Enterprise tax accounting methods and requirements to align to James Hardie accounting methods (i.e. deferred taxes)
FRC-0231 | Finance & Accounting | Income Tax | Tax Compliance | Obtain tax depreciation information/schedules for all required assets as of transaction close
FRC-0232 | Finance & Accounting | Income Tax | Tax Compliance | Obtain and file Enterprise historical tax filing and audit data to James Hardie (electronic and paper)
FRC-0233 | Finance & Accounting | Income Tax | Tax Compliance | Assess Enterprise tax systems and determine integration plan
FRC-0234 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Develop transfer pricing documentation for new intercompany flows | High | Treasury
FRC-0235 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Analyze tax attribute carryforwards (NOLs, credits) for acquired entity | High
FRC-0236 | Finance & Accounting | Income Tax | Transfer Pricing & Intercompany (NEW) | Assess Section 382/383 limitations on acquired tax attributes | High | Legal
FRC-0214 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Design controls for new intercompany transactions | High | Operational Accounting
FRC-0215 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Assess IT General Controls (ITGC) for acquired systems | High | IT
FRC-0216 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Conduct fraud risk assessment for combined entity | High | Finance Leadership
FRC-0220 | Finance & Accounting | Internal Controls | Controls for Integration Activities (NEW) | Assess purchase accounting controls and journal entry review | High | Consolidation
FRC-0200 | Finance & Accounting | Internal Controls | Internal Audit | Assist management by evaluating the design and effectiveness of critical operating controls and estblish remediation strategies.
FRC-0201 | Finance & Accounting | Internal Controls | Internal Audit | Develop an understanding of Fermacell's SOX and IA programs and prior year SOX/IA results.
FRC-0202 | Finance & Accounting | Internal Controls | Internal Audit | Plan 2018 Fermacell controls testing strategy to support 2018 EY substantive audit activities
FRC-0203 | Finance & Accounting | Internal Controls | Internal Audit | Assist management with designing and implementing acquisition transaction controls (e.g., FCR, Treasury, Tax)
FRC-0204 | Finance & Accounting | Internal Controls | Internal Audit | Understand requirements defined in TSA and perform a risk evaluation.
FRC-0205 | Finance & Accounting | Internal Controls | Internal Audit | Determine IA staffing/cosource needs including longer term audit department structure and short term needs for SOX requirements.
FRC-0207 | Finance & Accounting | Internal Controls | Internal Audit | Execute 2018 Fermacell controls testing, to support EY substantive audit activities.
FRC-0208 | Finance & Accounting | Internal Controls | Internal Audit | Conduct New Co. risk assessment while leveraging Fermacell risk assessment results.
FRC-0209 | Finance & Accounting | Internal Controls | Internal Audit | Define the future SOX plan for New Co.
FRC-0210 | Finance & Accounting | Internal Controls | Internal Audit | Refine existing 302 certification plan
FRC-0211 | Finance & Accounting | Internal Controls | Internal Audit | Conduct a TSA compliance audit for high risk areas.
FRC-0212 | Finance & Accounting | Internal Controls | Internal Audit | Execute audits supporting regulatory compliance including EU Safe Harbor and Conflict Minerals)
FRC-0213 | Finance & Accounting | Internal Controls | Internal Audit | Evaluate and purchase an IA/SOX document retention tool.
FRC-0138 | Finance & Accounting | Operational Accounting | Accounts payable | Understand current A/P processing (domestic and international)
FRC-0139 | Finance & Accounting | Operational Accounting | Accounts payable | Identify responsibility for payables processing for Day 1
FRC-0142 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Identify responsibility for processing time and expenses
FRC-0143 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Determine and develop approach to time and expense reimbursement (e.g., through direct deposit, with normal paycheck, or separate run)
FRC-0144 | Finance & Accounting | Operational Accounting | Accounts payable - travel and entertainment reimbursement and employee policies | Communicate travel and expense policies and procedures corporate wide
FRC-0146 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Develop the combined invoicing process under NewCo
FRC-0147 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Determine intracompany invoicing currency
FRC-0148 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Generate an update letter for customers with NewCo name change. Coordinate with company announcement.
FRC-0149 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Develop communication plan for sales team for invoicing practices
FRC-0150 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Determine updated sales tax requirements
FRC-0151 | Finance & Accounting | Operational Accounting | Accounts receivable - billing | Define returns and billing adjustment policies
FRC-0152 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Understand differences in credit policies
FRC-0153 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Review credit files and evaluate major creditors for any new exposures
FRC-0154 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Evaluate credit limits for common customers and determine the combined company credit limit
FRC-0155 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Standardize the credit approval and documentation process
FRC-0156 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Identify differences in "account overdue" definition and standardize
FRC-0157 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Identify differences in the collection process and standardize
FRC-0158 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Consolidate credit collections agents
FRC-0159 | Finance & Accounting | Operational Accounting | Accounts receivable - credit and collections | Establish a consistent write off policy
FRC-0169 | Finance & Accounting | Operational Accounting | Cash management | Perform bank account reconciliation and consolidation
FRC-0170 | Finance & Accounting | Operational Accounting | Cash management | Update and finalize Day 1 banking requirements
FRC-0171 | Finance & Accounting | Operational Accounting | Cash management | Ensure Day 1 funding and purchase accounting
FRC-0172 | Finance & Accounting | Operational Accounting | Cash management | Identify long-term cash management responsibility (signing, bank notification) and implement cash management functionality (bank, auto or manual)
FRC-0173 | Finance & Accounting | Operational Accounting | Cash management | Identify any 3rd party debt and payment requirements
FRC-0198 | Finance & Accounting | Operational Accounting | Contracts | Review any exclusive purchasing agreements or preferred supplier for conflicts
FRC-0199 | Finance & Accounting | Operational Accounting | Contracts | Review payment terms and determine what actions, if any, need to take place
FRC-0184 | Finance & Accounting | Operational Accounting | Fixed assets | Assess current but not yet started projects
FRC-0185 | Finance & Accounting | Operational Accounting | Fixed assets | Determine if a fixed asset inventory is required and implement if necessary (coordinate with IT for IT hardware)
FRC-0186 | Finance & Accounting | Operational Accounting | Fixed assets | Develop approach to managing assets that will be disposed of on Day 1, if applicable
FRC-0187 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize procedures for asset retirement and disposal
FRC-0188 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize capitalization policies and procedures
FRC-0189 | Finance & Accounting | Operational Accounting | Fixed assets | Standardize depreciation methods
FRC-0120 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Obtain policies and procedures on monthly close and close schedule with cut-offs and timing
FRC-0121 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Identify and manage differences in chart of accounts
FRC-0122 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Develop the approach to managing multiple chart of accounts
FRC-0123 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Identify tools needed to perform the monthly consolidation
FRC-0124 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Establish the interim combined company financial close calendar
FRC-0125 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Develop contingency plan based upon different deal close date scenarios
FRC-0126 | Finance & Accounting | Operational Accounting | General Ledger - close the books | Assess opportunity for close process improvement
FRC-0177 | Finance & Accounting | Operational Accounting | Intercompany elimination | Perform inventory of I/C relationships
FRC-0178 | Finance & Accounting | Operational Accounting | Intercompany elimination | Assess integration impact on current and expected intercompany transactions
FRC-0179 | Finance & Accounting | Operational Accounting | Intercompany elimination | Understand intercompany types of transactions (calendar, out-of-balance materiality threshold, settlement, etc.)
FRC-0180 | Finance & Accounting | Operational Accounting | Intercompany elimination | Understand multi-arrangements transactions and assess materiality, if any
FRC-0181 | Finance & Accounting | Operational Accounting | Intercompany elimination | Assess current process for capturing intercompany activity and assess applicability to current business requirements
FRC-0182 | Finance & Accounting | Operational Accounting | Intercompany elimination | Determine if manual workaround is required to eliminate complex intercompany transactions between James Hardie and Fermacell
FRC-0183 | Finance & Accounting | Operational Accounting | Intercompany elimination | Create new intercompany trading partners and accounts
FRC-0195 | Finance & Accounting | Operational Accounting | Inventory | Assess current inventory policies and processes (reserves, returns, costing)
FRC-0196 | Finance & Accounting | Operational Accounting | Inventory | Align material differences in accounting policy
FRC-0197 | Finance & Accounting | Operational Accounting | Inventory | Conduct inventory valuations, as required
FRC-0130 | Finance & Accounting | Operational Accounting | Payroll | Assess current state processes
FRC-0131 | Finance & Accounting | Operational Accounting | Payroll | Confirm listing of employees census, geographical location and legal entity structuring
FRC-0132 | Finance & Accounting | Operational Accounting | Payroll | Plan enrollment procedures for Day 1 acquired employees
FRC-0133 | Finance & Accounting | Operational Accounting | Payroll | Determine systems required to manage Fermacell payroll functions of Day 1
FRC-0134 | Finance & Accounting | Operational Accounting | Payroll | Develop interim operating model for Day 1
FRC-0135 | Finance & Accounting | Operational Accounting | Payroll | Understand downstream benefit accounting impacts based on HR decisions
FRC-0190 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Identify all projects and initiatives (capex and other) in progress or about to be launched and review with respect to NewCo structure and objectives. Rationalize if required
FRC-0191 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Identify critical projects and launches that need to managed through the transition to minimize risk of failure
FRC-0192 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Review all current major projects for compliance with delivery dates
FRC-0193 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Review all current major projects for cost status versus budget and forecast
FRC-0194 | Finance & Accounting | Operational Accounting | Projects and Initiatives | Ensure project reporting systems provide adequate management information
FRC-0160 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify revenue recognition methodology differences between companies and determine Day 1 policy
FRC-0161 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Determine how any revenue recognition methodology changes impact the current sales and contracting process
FRC-0162 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Update standard contracts, as necessary
FRC-0163 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Determine combined company ales model and cummuncate with field sales team
FRC-0164 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify any issues between the proposed sales model to the proposed revenue recognition methodology
FRC-0165 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Identify any contracting conflicts caused by the proposed sales model
FRC-0166 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Work with Sales Management to revise sales models and methodologies for revenue recognition and contracting
FRC-0167 | Finance & Accounting | Operational Accounting | Revenue recognition policies | Train and implement amended receivable policies
FRC-0174 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Identify IT requirements for Day 1 wire transfers and implement (auto or manual)
FRC-0175 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Update and communicate new signature process
FRC-0176 | Finance & Accounting | Operational Accounting | Wire and electronic transfers | Identify required vendor wire transfers and confirm set up
FRC-0279 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Inventory Enterprise banking partners, accounts, and bank contacts
FRC-0280 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Document the Enterprise / James Hardie combines bank structure
FRC-0281 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine officers authorized to sign bank mandates
FRC-0282 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine associates authorized to process electronic payment and sign checks
FRC-0283 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Review the account analysis statements to determine what bank services are utilized.
FRC-0284 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Determine recent cash balances for all banks
FRC-0285 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Open new bank accounts to support new tax structure and replace existing bank accounts
FRC-0286 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | Provide process change communication to banks providing services on Day One
FRC-0287 | Finance & Accounting | Treasury & Risk Mgmt | Bank Relationship and Account Management | After new boards are established, prepare bank resolutions authorized Enterprise / James Hardie officers
FRC-0297 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Identify and assume control of Enterprise cash globally
FRC-0298 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine combined James Hardie global cash forecasting and reporting processes
FRC-0299 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine daily cash concentration and positioning processes for combined James Hardie
FRC-0300 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Identify all Enterprise ACH debit / credit arrangements (tax, vendor payments)
FRC-0301 | Finance & Accounting | Treasury & Risk Mgmt | Cash Management | Determine procedures and controls for executing electronic fund transfers (EFTs)
FRC-0289 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Determine if Enterprise issues Corporate credit cards / p-cards to employees.
FRC-0290 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company.
FRC-0291 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Review the process to interface credit card with ERP and other systems
FRC-0292 | Finance & Accounting | Treasury & Risk Mgmt | Credit Cards | Sign a new contract with the credit card company (incumbent or new)
FRC-0323 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Refinance or restructure acquired company debt as needed | High | Legal
FRC-0324 | Finance & Accounting | Treasury & Risk Mgmt | Debt & Capital Structure (NEW) | Notify lenders and rating agencies of transaction close | High | Investor Relations
FRC-0303 | Finance & Accounting | Treasury & Risk Mgmt | Determine how the new intercompany structure will impact foreign exchange exposures. | Determine the best way to hedge the combined foreign exchange exposures
FRC-0316 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | Information regarding new associates that will be granted equity options in the first quarter
FRC-0317 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | Copy of all stock option agreements - PSA/U, RSA/U, SSR…
FRC-0318 | Finance & Accounting | Treasury & Risk Mgmt | Equity Compensation | List of all employees receiving options, type of option being granted, and number of options / shares
FRC-0272 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Develop a detailed cash flow forecast for pre-acquisition and year one activities
FRC-0273 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Identify Enterprise and Xella outstanding intercompany loans and settlement plan
FRC-0274 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Determine interim working capital needs for combined James Hardie
FRC-0275 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Assess global liquidity needs
FRC-0276 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Based upon cash flow and inter-company payments determine the optimal interest rat SWAP structure.
FRC-0277 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Determine requirements for debt instruments (covenants, interest rate swaps) and associated procedures
FRC-0278 | Finance & Accounting | Treasury & Risk Mgmt | Financing and Investing | Identify and evaluate Enterprise procedures for letters of credit execution and monitoring, as needed
FRC-0302 | Finance & Accounting | Treasury & Risk Mgmt | Foreign Exchange | Determine the non-functional currency balance sheet and cash flow hedge exposures.
FRC-0304 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Review and evaluate Enterprise exposures insured, limits and deductibles.
FRC-0305 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Obtain a list of current and former legal entities that need to be insured. If not in the United States, please identify the country incorporated.
FRC-0306 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Five year history of all open and closed insurance claims. If claims are open, please provide a status update.
FRC-0307 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Property - list of all locations detailing the address and values by locations (building value, inventory, contents, BI, CBI, and extra expense).
FRC-0308 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | COPE information for all locations with values in excess of $1M
FRC-0309 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Property engineering, carrier inspection, and boiler/machinery inspection reports.
FRC-0310 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Description of interdependencies between locations.
FRC-0311 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of out-sourced manufacturing relationships including description, related sales/purchase volumes, and process criticality.
FRC-0312 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of certificates of insurance.
FRC-0313 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Projected international payroll and employee headcount by country.
FRC-0314 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Foreign sales to the US, sales from the US to other countries, and sales from international locations to other countries.
FRC-0315 | Finance & Accounting | Treasury & Risk Mgmt | Insurance | Schedule of import/export dollar values by product, geography, and type of vessel used to ship product
FRC-0293 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Determine if Enterprise accepts credit card payments from customers
FRC-0294 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Determine if we should continue to use the same credit card / p-card company or should we use a new credit card company.
FRC-0295 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Review the process to interface credit card with ERP and other systems
FRC-0296 | Finance & Accounting | Treasury & Risk Mgmt | Merchant Card Processing | Sign a new contract with the credit card company (incumbent or new)
FRC-0268 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Complete Day One staffing requirements for combined Treasury
FRC-0269 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Determine Gaps in Treasury's polices and procedures
FRC-0270 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Establish combined Treasury policies and controls
FRC-0271 | Finance & Accounting | Treasury & Risk Mgmt | Organization and Governance | Train Enterprise staff on Day One Treasury processes, as needed
FRC-0319 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Assess working capital requirements for combined entity | High | FP&A
FRC-0320 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Analyze cash flow and debt obligations to optimize liquidity | High | FP&A
FRC-0321 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Monitor covenant compliance for combined debt structure | High | Legal, FP&A
FRC-0322 | Finance & Accounting | Treasury & Risk Mgmt | Working Capital & Liquidity (NEW) | Develop 13-week cash flow forecast for combined entity | High | FP&A
FRC-0388 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Inventory AI tools and automation systems used by target | Medium | IT, Operations
FRC-0389 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Assess AI-related risks (privacy, IP, bias, employment) | Medium | Legal, HR
FRC-0390 | IT | Cybersecurity & Data Privacy | AI & Automation Governance | Review AI vendor contracts and data usage terms | Medium | Legal, Procurement
FRC-0375 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Conduct cybersecurity risk assessment of target's IT infrastructure | High | IT
FRC-0376 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Inventory all IT systems, applications, and data repositories | High | IT
FRC-0377 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Review target's data breach history and incident response procedures | High | Legal, IT
FRC-0378 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Assess network security controls and vulnerability management practices | High | IT
FRC-0379 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Review third-party vendor cybersecurity practices and contracts | High | Procurement, Legal
FRC-0380 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Identify cyber insurance coverage and gaps | High | Treasury, Legal
FRC-0381 | IT | Cybersecurity & Data Privacy | Cybersecurity Risk Assessment | Develop IT system integration security plan | High | IT
FRC-0382 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Inventory personal data collected by target (customers, employees, vendors) | High | Legal, HR
FRC-0383 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Assess compliance with GDPR, CCPA, and other applicable privacy laws | High | Legal
FRC-0384 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Review data processing agreements with third parties | Medium | Legal, Procurement
FRC-0385 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Identify cross-border data transfer mechanisms and requirements | High | Legal, IT
FRC-0386 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Review privacy policies and customer consent mechanisms | Medium | Legal, Marketing
FRC-0387 | IT | Cybersecurity & Data Privacy | Data Privacy Compliance | Assess data retention policies and practices | Medium | Legal, IT
FRC-0360 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Conduct interviews with finance workstream leads to understand current finance processes
FRC-0361 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Identify Finance integration value capture targets
FRC-0362 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Develop detailed qualitative/quantitative business cases for Finance value capture initiatives
FRC-0363 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Review value capture initiatives with finance workstream leads
FRC-0364 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Develop a final validated list of value capture initiatives for the finance function
FRC-0365 | Integration Management | Baselining | Identification of Finance Value Capture Opportunities | Review business cases and validate value capture targets with workstream leads
FRC-0366 | Integration Management | Baselining | Planning for Value Capture | Develop detailed workplans for execution of each approved value driver initiative
FRC-0367 | Integration Management | Baselining | Planning for Value Capture | Define metrics to track progress towards reaching value capture targets
FRC-0368 | Integration Management | Baselining | Planning for Value Capture | Develop mechanism to report on value capture activities
FRC-0369 | Integration Management | Baselining | Planning for Value Capture | Develop high level milestone plan showing value capture targets at various points along the integration timeline
FRC-0370 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Develop consolidated list of value capture initiatives identified by individual functions
FRC-0371 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Consolidate business cases developed by individual functions into master
FRC-0372 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Validate business cases for completeness and validate any assumptions made
FRC-0373 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Develop a consolidated value capture model across all functions
FRC-0374 | Integration Management | Baselining | Validation of value capture initiatives for other functions | Validate consolidated value capture targets with cost synergies identified in deal model
FRC-0436 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Develop integration communication plan (internal and external) | High | Comms, HR
FRC-0437 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Establish integration governance structure (PMO, Steering Committee) | High | Executive Leadership
FRC-0438 | Integration Management | Integration Budget & Tracking | Communication & Change Management | Define escalation paths and decision-making protocols | High | PMO
FRC-0418 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Develop comprehensive integration budget by workstream | High | All Workstreams
FRC-0419 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Identify one-time integration costs vs. ongoing run-rate costs | High | FP&A
FRC-0420 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Establish integration cost tracking and reporting cadence | High | FP&A, PMO
FRC-0421 | Integration Management | Integration Budget & Tracking | Integration Budget Planning | Define cost approval thresholds and governance process | High | Finance Leadership
FRC-0431 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Define integration success metrics and KPIs | High | PMO, FP&A
FRC-0432 | Integration Management | Integration Budget & Tracking | Integration KPIs & Success Metrics | Establish baseline measurements for all KPIs | High | All Workstreams
FRC-0422 | Integration Management | Integration Budget & Tracking | Stranded Costs Management | Identify potential stranded costs from TSA exits | High | TSA, FP&A
FRC-0423 | Integration Management | Integration Budget & Tracking | Stranded Costs Management | Develop stranded cost mitigation plan | High | All Functions
FRC-0425 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Develop synergy tracking model aligned with deal model assumptions | High | FP&A, Corp Dev
FRC-0426 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Define synergy categories (cost, revenue, capital) | High | FP&A
FRC-0427 | Integration Management | Integration Budget & Tracking | Synergy Tracking | Establish synergy measurement methodology and baseline | High | FP&A
FRC-0400 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Conduct ESG due diligence on target company | High | Legal, Operations
FRC-0401 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Identify material ESG risks and liabilities (environmental, social, governance) | High | Legal, Operations
FRC-0402 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Review environmental permits, compliance history, and remediation obligations | High | Legal, Facilities
FRC-0403 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Assess target's carbon footprint and emissions data | Medium | Operations
FRC-0404 | Legal / Compliance | ESG & Sustainability | ESG Assessment & Due Diligence | Review labor practices, health & safety records, and supply chain standards | High | HR, Operations
FRC-0405 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Identify applicable ESG reporting requirements (EU CSRD, SEC Climate, TCFD) | High | Legal, Finance
FRC-0406 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Assess combined company's ESG disclosure obligations | High | Legal, Investor Relations
FRC-0407 | Legal / Compliance | ESG & Sustainability | Regulatory Compliance | Review target's existing ESG reports and ratings | Medium | Investor Relations
FRC-0242 | Operations | Facilities & Indirect Sourcing | Facilities | Complete diligence on existing Real Estate organization
FRC-0243 | Operations | Facilities & Indirect Sourcing | Facilities | Design Day One and interim state organization structure
FRC-0244 | Operations | Facilities & Indirect Sourcing | Facilities | Estimate synergies related to Day One and interim organization structure
FRC-0245 | Operations | Facilities & Indirect Sourcing | Facilities | Inventory and map total real estate holdings
FRC-0246 | Operations | Facilities & Indirect Sourcing | Facilities | Collaborate with org design team to understand facility requirements
FRC-0247 | Operations | Facilities & Indirect Sourcing | Facilities | Complete review of corporate locations for optimization planning
FRC-0248 | Operations | Facilities & Indirect Sourcing | Facilities | Review leases on properties that may be exited post-transaction close to determine if early termination provision exists
FRC-0249 | Operations | Facilities & Indirect Sourcing | Facilities | Determine landlords requiring notification or consent letters prior to transaction close
FRC-0250 | Operations | Facilities & Indirect Sourcing | Facilities | Notifications and consent letters for required landlords sent out and consent letters received
FRC-0251 | Operations | Facilities & Indirect Sourcing | Facilities | Determine go-forward future data management tool for Real Estate of combined company
FRC-0252 | Operations | Facilities & Indirect Sourcing | Facilities | Assume lease ownership for sites that are leased by Xella and are being transferred to James Hardie
FRC-0253 | Operations | Facilities & Indirect Sourcing | Facilities | Ensure flawless transition and harmonization of facilities management and maintenance
FRC-0254 | Operations | Facilities & Indirect Sourcing | Facilities | Ensure appropriate security access changes are reflected in facilities
FRC-0260 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Review and rationalize current indirect spend
FRC-0261 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Complete review / diligence on current vendor sourcing and outsourcing contracts
FRC-0262 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Revised synergy & one-time cost estimates based on diligence findings
FRC-0263 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Review existing vendors for capabilities, quality, and compliance with corporate standards
FRC-0264 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Create and implement a supplier vendor certification process
FRC-0265 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Achieve optimal vendor sourcing for combined company
FRC-0266 | Operations | Facilities & Indirect Sourcing | Indirect Sourcing | Assess current state metrics and reporting process
FRC-0001 | TSA / Deal Structure | TSA | Assessment of Service needs | Review existing TSA schedules developed by Xella
FRC-0002 | TSA / Deal Structure | TSA | Assessment of Service needs | Develop a TSA tracker listing out for each TSA, the scope of services, related function, service fees, duration, location, TSA owners etc.
FRC-0003 | TSA / Deal Structure | TSA | Assessment of Service needs | Conduct interviews with each function at Fermacell to identify services currently provided by Xella to Fermacell
FRC-0004 | TSA / Deal Structure | TSA | Assessment of Service needs | Determine services provided by Xella teams that are not transferring with the deal
FRC-0005 | TSA / Deal Structure | TSA | Assessment of Service needs | Determine services provided by Xella to Fermacell that could be provided in-house by Fermacell
FRC-0006 | TSA / Deal Structure | TSA | Assessment of Service needs | Conduct interviews with James Hardie functions to determine services that James Hardie can provide to replace those provided by Xella
FRC-0007 | TSA / Deal Structure | TSA | Assessment of Service needs | Develop list if services for which Transition Services Agreements will be needed
FRC-0008 | TSA / Deal Structure | TSA | Assessment of Service needs | Identify gaps between services in the TSA schedule provided by Xella and those identified through interviews with functional leads from James Hardie and Fermacell
FRC-0009 | TSA / Deal Structure | TSA | Assessment of Service needs | Validate the services for which support will be required through TSAs with each functional lead at Fermacell, James Hardie, and Xella
FRC-0018 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Identify TSA owners from Xella (Service Provider) and James Hardie/Fermacell (Service Recipient)
FRC-0019 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Develop a TSA governance process based on terms in the Form of Transition Services
FRC-0020 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Review the governance process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties
FRC-0021 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Develop a process to calculate TSA fees on a monthly basis and to generate invoices
FRC-0022 | TSA / Deal Structure | TSA | Governance and Invoicing Process | Review the invoicing process with functional leads from James Hardie, Fermacell and Xella and get agreement from all parties
FRC-0010 | TSA / Deal Structure | TSA | Schedule of TSA services | Conduct interviews with Fermacell functional leads to develop detailed scope of services to be provided under each TSA
FRC-0011 | TSA / Deal Structure | TSA | Schedule of TSA services | Identify locations at which TSAs are needed as well as TSA duration
FRC-0012 | TSA / Deal Structure | TSA | Schedule of TSA services | Legal team to draft TSA schedules for each service that Xella will need to provide, if TSA schedule does not already exist
FRC-0013 | TSA / Deal Structure | TSA | Schedule of TSA services | Legal team to modify existing TSA schedules based on feedback from functional leads from James Hardie and Fermacell functional leads
FRC-0014 | TSA / Deal Structure | TSA | Schedule of TSA services | Discuss updated TSA schedule with Xella through executive steering committee meetings
FRC-0015 | TSA / Deal Structure | TSA | Schedule of TSA services | Modify TSA schedules as needed based on feedback from functional leads
FRC-0016 | TSA / Deal Structure | TSA | Schedule of TSA services | Review modified TSA schedules with functional leads from James Hardie, Fermacell and Xella and get sign off from all parties
FRC-0017 | TSA / Deal Structure | TSA | Schedule of TSA services | Draft final (execution version) of TSA schedule to be signed at deal close
FRC-0023 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Define TSA exit criteria and transition milestones for each service
FRC-0024 | TSA / Deal Structure | TSA | TSA Exit Planning (NEW) | Identify stranded costs associated with TSA exits | High | FP&A

## PRD FR Traceability
PRD Requirement | Requirement Name | How Checklist Maps | Coverage Detail
FR-4 | Multi-Level Taxonomy | All workstreams map to L1→L2→L3 hierarchy | 6 L1 domains, 12 L2 workstreams, 75 L3 sections
FR-5 | Digitization of Legacy Lists | All 443 line items assigned unique IDs | 443 items with IDs FRC-0001 through FRC-0443
FR-6 | Industry-Specific Variants | NEW sections added (Cyber, ESG, Integration Budget) | 3 new workstreams, multiple NEW sections in existing
FR-7 | Deal-Level Scope Selection | Applicable to Acquirer/Target columns enable scoping | Per-item Yes/No flags for each deal party
FR-8 | Line-Item Status Input | Status and Importance columns on each item | 4 status values, 3 importance levels
FR-9 | Time Tracking vs Key Dates | Phase/Milestone mapped to Day 1, Day 60-120, Year 1-2 | 4 milestone phases across all items
FR-14 | Context-Aware Task Adjustment | TSA_Relevant flag enables auto-graying per FR-18 | 29 TSA-flagged items
FR-16 | TSA Determination | Dedicated TSA workstream with 4 sections | 29 TSA items covering assessment through exit
FR-10 | Weekly Status Update | Dependencies & comments columns support updates | 114 items with cross-team dependencies
FR-11 | Aggregated Views | Pivot views by phase, importance, domain, workstream | 6 analytical sheets in this workbook
FR-26 | Navigation & Views | Filterable master list + domain/phase/importance views | Auto-filters on master list and critical path
FR-27 | Dashboards (MVP) | Phase timeline + importance matrix provide summary data | Summary counts feed dashboard visualizations